## Q3 dates
SLA Report of the dates 14 -Aug-2022 to 13-Nov-2022
| Sheet | Description | SLA Scope
| SLA-1 | Submission of all the deliverables | Deliverables related to Transition, Design and Development and O& M
| SLA-2 | Defect count in UAT environment | The scope of this SLA includes weighted average count (WAC) of defects identified in Production environment.
| SLA-3 | TAT for defects in Production environment | Turn Around Time (TAT) for fixing defects, identified in the Production environment and classified as per the 'Defect Matrix' above.
| SLA-4 | Defect count in Production environment | The scope of this SLA includes defects WAC identified in the Production environment.
| SLA-5 | Upgrade of applications to support the (N-1) version of technology components | This SLA is intended to determine the percentage of applications that have been upgraded to support the (N-1) version of technology components in the production and non-production environments, which hold the latest stable released version of the technology component(s). Once the (N-1) technology components are provided by the NHA in a year, the MSP will have to ensure that all applications are upgraded accordingly in the remaining duration of the year.
| SLA-6 | Mobilization of all selected ‘Core’ resources as per the timeline | This SLA applies to team mobilization and deployment of selected Core resources, within 15 days from date of contract signing and will remain applicable till the end of contract including extension period.
| SLA-7 | Mobilization of 100% resources as per the timeline | This SLA applies to team mobilization and deployment of selected Core resources, within 15 days from date of contract signing and will remain applicable till the end of contract including extension period.
| SLA-8 | No. of Resource replacement in a Quarter (for ‘Core Resources’) | This SLA will be applicable to all the ‘Core resources’ to whom replacement is initiated by the MSP.
| SLA-9 | Number of Resource replacement in a Quarter for (Non ‘Core Resources’) | This SLA will be applicable to all the” O&M resources” for whom replacement is initiated by the MSP.
| SLA-10 | Minimum overlap period during resource replacement | This SLA will be applicable for all resources, for whom replacement is initiated by the MSP. This SLA is to measure the ‘overlap period’ between an outgoing MSP resource and the incoming MSP resource. A minimum of 2 business weeks is necessary to ensure adequate knowledge transition and project tasks handover.
| SLA-11 | Minimum resource availability (8*5 support resources’) | This SLA applies to the availability of all resources (except designated 24*7 support resources) in a month. The attendance logged by each resource will be used to compute monthly availability.
| SLA-12 | Minimum resource availability (‘24*7 support resources’) | This SLA will be applicable to designated ‘24*7 Support resource’. The MSP is required to maintain the level of staffing for these resources, as required by the NHA. The attendance logged by the designated 24*7 Support resources’ will be used to compute the monthly availability.
| SLA-13 | Application Uptime | The scope of the SLA includes all NHA applications
| SLA-14 | Application Performance | Response time of all the NHA applications.
| SLA-15 | Application Incident Resolution | Incident categorization and turnaround time for different types of incidents will be mutually decided by the NHA and the MSP.
Facts & Assumptions
| 1 | One Business week is Five working days
| 2 | PM1 milestone sign-off date is 15th Sep 2022
| 3 | Planned O&M resource deployment date for SLA calculation is 14 Aug 2022
| 4 | Effective working days for SLA 11 includes all Monday to Friday (excluding any and all public or MSP holidays)
Incidence SLA Matrix
| Severity | Incident SLA matrix (response time) | Incident SLA matrix (resolution time)
| Blocker | P1 - 15 Mins | P1 - 8 Hours
| Critical | P2 - 2 Hours | P2 - 24 Hours
| Major | P3 - 16 Hours | P3 - 48 Hours
| Minor | P4 - 24 Hours | P4 - 72 Hours
|  | N/A* - Dependency on third party vendor | N/A* - Dependency on third party vendor

## SLA-1
SLA 001- Submission of all the Deliverables (Deliverables related to Transition, Design and Development and O& M )
| SI | Deliverable | Track | Quarter | Contractual Date | Submission Date | SLA Calculation | Approval Date
| 1 | Detailed Transition Plan (to be submitted by T+30 days) | C1 | 3 | 2022-03-15 | 2022-03-11 | -4
| 2 | Gap Analysis Report | C1 | 3 | 2022-05-15 | 2022-08-08 | 85
| 3 | Operational Manual for Sandbox on boarding and Exit Process | C1 | 3 | 2022-05-15 | 2022-07-07 | 53
| 4 | FRS, SRS, HLD, LLD and User Experience Enhancement Report of existing/ LIVE Building Blocks | C1 | 3 | 2022-05-15 | 2022-08-08 | 85
| 5 | FRS, SRS, HLD, LLD and User Experience Enhancement Report of New Building Blocks | C1 | 3 | 2022-05-15 | 2022-05-09 | -6
| 8 | Service level compliance reports generated from SLA Monitoring Tool. | C2 | 3 | 2022-11-15 | 2022-11-14 | -1
| 9 | Following deliverables are required on regular basis: • Updated system design documents, specifications • Latest source code, application deployment files, configuration files for entire solution • Updated user manuals, administration manuals, training manuals etc. • Software change logs etc. • Adherence to the proposed Transition and Data Migration Plan • Help Desk/ Contact Center Status Report • Sandbox Integration Report • WASA Certification Report | C2 | 3 | 2022-11-15 | 2022-11-14 | -1

## SLA-2
SLA 002- Defect count in UAT environment
No UAT environment defined in existing application landscape.

## SLA-3
SLA 003- TAT for defects in Production environment
In this Quarter (Effective date for SLA: PM1 approval date)
| Sr No. | Ticket ID | Blocks | Created Date | Month | Severity | Resolution Date | Days Variance | Applied Severity Level |  | Blocker | Critical | Major | Minor
| 1 | SDFI-795 | ABHA ID | 2022-09-14 12:20 | 9 | Blocker | 2022-10-03 09:57 | 18.9007 | 4 | Aug | NA | NA | NA | NA
| 2 | SDFI-797 | PHR APP | 2022-09-15 06:07 | 9 | Blocker | 2022-10-03 14:07 | 18.3333 | 4 | Sep | 49 | 13 | 6 | 2
| 3 | SDFI-798 | PHR APP | 2022-09-15 06:14 | 9 | Blocker | 2022-11-07 09:43 | 53.1451 | 18 | Oct | 24 | 17 | 11 | 1
| 4 | SDFI-799 | PHR APP | 2022-09-15 06:19 | 9 | Blocker | 2022-10-26 17:04 | 41.4479 | 12 | Nov | 7 | 6 | 8 | 4
| 5 | SDFI-800 | PHR APP | 2022-09-15 06:24 | 9 | Blocker | 2022-10-03 14:44 | 18.3472 | 4 | Total | 80 | 36 | 25 | 7
| 6 | SDFI-801 | PHR APP | 2022-09-15 06:30 | 9 | Blocker | 2022-11-04 13:34 | 50.2944 | 16
| 7 | SDFI-807 | ABHA ID | 2022-09-15 12:58 | 9 | Major | 2022-10-26 16:20 | 41.1403 | 2
| 8 | SDFI-809 | PHR APP | 2022-09-15 16:10 | 9 | Blocker | 2022-09-23 11:49 | 7.8187 | 0
| 9 | SDFI-810 | ABHA ID | 2022-09-15 16:16 | 9 | Blocker | 2022-09-29 16:13 | 13.9979 | 2
| 10 | SDFI-811 | HIE-CM | 2022-09-15 16:22 | 9 | Blocker | 2022-10-26 17:04 | 41.0292 | 12
| 11 | SDFI-812 | PHR APP | 2022-09-15 16:27 | 9 | Blocker | 2022-09-19 10:52 | 3.7674 | 0
| 12 | SDFI-814 | PHR APP | 2022-09-15 16:48 | 9 | Blocker | 2022-10-06 13:06 | 20.8458 | 4
| 13 | SDFI-816 | PHR APP | 2022-09-15 16:56 | 9 | Blocker | 2022-09-30 13:23 | 14.8521 | 2
| 14 | SDFI-817 | ABHA ID | 2022-09-15 17:05 | 9 | Not Filled | Open | 157.2882 | NA
| 15 | SDFI-818 | PHR APP | 2022-09-15 17:11 | 9 | Blocker | 2022-09-23 11:57 | 7.7819 | 0
| 16 | SDFI-821 | PHR APP | 2022-09-15 17:15 | 9 | Blocker | 2022-10-04 22:36 | 19.2229 | 4
| 17 | SDFI-822 | ABHA ID | 2022-09-15 20:46 | 9 | Not Filled | Open | 157.1347 | NA
| 18 | SDFI-823 | PHR APP | 2022-09-15 20:50 | 9 | Not Filled | 2022-10-04 22:36 | 19.0736 | NA
| 19 | SDFI-824 | ABHA ID | 2022-09-16 06:05 | 9 | Blocker | 2022-09-29 15:52 | 13.4076 | 2
| 20 | SDFI-825 | HIE-CM | 2022-09-16 06:20 | 9 | Blocker | 2022-09-16 14:29 | 0.33958 | 0
| 21 | SDFI-826 | ABHA ID | 2022-09-16 13:20 | 9 | Blocker | 2022-10-03 10:03 | 16.8632 | 2
| 22 | SDFI-827 | ABHA ID | 2022-09-16 13:27 | 9 | Blocker | 2022-10-14 18:28 | 28.209 | 8
| 23 | SDFI-830 | ABHA ID | 2022-09-16 20:48 | 9 | Critical | 2022-11-03 14:08 | 47.7222 | 12
| 24 | SDFI-831 | PHR APP | 2022-09-17 11:23 | 9 | Blocker | 2022-09-23 12:03 | 6.0278 | 0
| 25 | SDFI-832 | HIE-CM | 2022-09-17 11:44 | 9 | Blocker | Open | 155.5111 | 58
| 26 | SDFI-833 | PHR APP | 2022-09-17 11:52 | 9 | Blocker | 2022-11-04 14:13 | 48.0979 | 16
| 27 | SDFI-834 | ABHA ID | 2022-09-17 12:40 | 9 | Blocker | 2022-10-25 22:45 | 38.4201 | 12
| 28 | SDFI-835 | ABHA ID | 2022-09-17 12:51 | 9 | Blocker | 2022-10-17 13:29 | 30.0264 | 8
| 29 | SDFI-837 | PHR APP | 2022-09-17 13:15 | 9 | Blocker | 2022-09-22 17:39 | 5.1833 | 0
| 30 | SDFI-838 | PHR APP | 2022-09-17 13:30 | 9 | Blocker | 2022-10-27 10:06 | 39.8583 | 12
| 31 | SDFI-841 | PHR APP | 2022-09-19 16:53 | 9 | Blocker | 2022-10-07 19:58 | 18.1285 | 4
| 32 | SDFI-842 | PHR APP | 2022-09-19 16:59 | 9 | Blocker | 2022-11-07 09:36 | 48.6924 | 16
| 33 | SDFI-845 | HIE-CM | 2022-09-19 17:51 | 9 | Blocker | 2022-10-26 17:04 | 36.9674 | 10
| 34 | SDFI-846 | HIE-CM | 2022-09-19 18:16 | 9 | Blocker | 2022-10-26 17:03 | 36.9493 | 10
| 35 | SDFI-847 | PHR APP | 2022-09-19 18:34 | 9 | Blocker | 2022-09-29 16:18 | 9.9056 | 0
| 36 | SDFI-848 | PHR APP | 2022-09-19 19:31 | 9 | Blocker | 2022-09-23 21:03 | 4.0639 | 0
| 37 | SDFI-853 | HIE-CM | 2022-09-20 14:26 | 9 | Not Filled | 2022-09-27 16:04 | 7.0681 | NA
| 38 | SDFI-854 | ABHA ID | 2022-09-20 15:11 | 9 | Not Filled | 2022-10-10 13:50 | 19.9437 | NA
| 39 | SDFI-855 | PHR APP | 2022-09-20 15:32 | 9 | Critical | 2022-10-01 10:35 | 10.7937 | 0
| 40 | SDFI-857 | PHR APP | 2022-09-20 15:55 | 9 | Critical | 2022-10-31 15:52 | 40.9979 | 10
| 41 | SDFI-861 | PHR APP | 2022-09-21 09:58 | 9 | Major | 2022-09-27 18:47 | 6.3674 | 0
| 42 | SDFI-862 | HFR | 2022-09-21 10:53 | 9 | Major | 2022-10-08 15:21 | 17.1861 | 0
| 43 | SDFI-863 | HIE-CM | 2022-09-21 11:37 | 9 | Critical | 2022-09-27 12:49 | 6.05 | 0
| 44 | SDFI-867 | HIE-CM | 2022-09-21 14:29 | 9 | Critical | 2022-11-04 15:48 | 44.0549 | 10
| 45 | SDFI-868 | HIE-CM | 2022-09-21 14:41 | 9 | Critical | 2022-09-29 16:20 | 8.0687 | 0
| 46 | SDFI-869 | PHR APP | 2022-09-21 15:07 | 9 | Critical | 2022-09-22 10:09 | 0.79306 | 0
| 47 | SDFI-870 | ABHA ID | 2022-09-21 16:25 | 9 | Blocker | 2022-10-03 14:08 | 11.9049 | 0
| 48 | SDFI-873 | HIE-CM | 2022-09-22 09:32 | 9 | Blocker | 2022-10-06 10:37 | 14.0451 | 2
| 49 | SDFI-874 | PHR APP | 2022-09-22 09:36 | 9 | Blocker | 2022-10-15 06:49 | 22.884 | 6
| 50 | SDFI-875 | HIE-CM | 2022-09-22 09:56 | 9 | Blocker | 2022-11-09 11:54 | 48.0819 | 16
| 51 | SDFI-876 | HIE-CM | 2022-09-22 10:00 | 9 | Blocker | 2022-11-03 11:55 | 42.0799 | 14
| 52 | SDFI-877 | ABHA ID | 2022-09-22 10:02 | 9 | Blocker | 2022-09-29 15:51 | 7.2424 | 0
| 53 | SDFI-881 | ABHA ID | 2022-09-22 14:30 | 9 | Not Filled | 2022-11-04 15:42 | 43.05 | NA
| 54 | SDFI-883 | ABHA ID | 2022-09-22 17:20 | 9 | Not Filled | 2022-11-07 14:43 | 45.891 | NA
| 55 | SDFI-884 | HIE-CM | 2022-09-23 12:32 | 9 | Critical | 2022-09-29 12:36 | 6.0028 | 0
| 56 | SDFI-888 | PHR APP | 2022-09-23 15:27 | 9 | Blocker | 2022-10-25 22:49 | 32.3069 | 10
| 57 | SDFI-889 | PHR APP | 2022-09-23 15:45 | 9 | Blocker | 2022-10-25 22:49 | 32.2944 | 10
| 58 | SDFI-890 | ABHA ID | 2022-09-23 21:00 | 9 | Blocker | 2022-10-26 17:09 | 32.8396 | 10
| 59 | SDFI-892 | HIE-CM | 2022-09-27 10:36 | 9 | Major | Open | 145.5583 | 23
| 60 | SDFI-893 | ABHA ID | 2022-09-27 10:58 | 9 | Minor | Open | 145.5431 | 20
| 61 | SDFI-894 | PHR APP | 2022-09-27 11:13 | 9 | Critical | Open | 145.5326 | 52
| 62 | SDFI-896 | PHR APP | 2022-09-27 11:51 | 9 | Critical | 2022-10-25 14:11 | 28.0972 | 4
| 63 | SDFI-897 | HIE-CM | 2022-09-27 12:22 | 9 | Critical | 2022-09-27 16:01 | 0.15208 | 0
| 64 | SDFI-901 | PHR APP | 2022-09-28 12:58 | 9 | Not Filled | 2022-10-25 11:12 | 26.9264 | NA
| 65 | SDFI-902 | PHR APP | 2022-09-28 13:43 | 9 | Not Filled | 2022-10-25 16:28 | 27.1146 | NA
| 66 | SDFI-909 | HIE-CM | 2022-09-29 09:43 | 9 | Critical | 2022-11-03 11:16 | 35.0646 | 8
| 67 | SDFI-910 | ABHA ID | 2022-09-29 10:22 | 9 | Blocker | 2022-09-29 14:05 | 0.15486 | 0
| 68 | SDFI-911 | PHR APP | 2022-09-29 10:38 | 9 | Blocker | 2022-10-07 19:33 | 8.3715 | 0
| 69 | SDFI-915 | HPR | 2022-09-29 11:20 | 9 | Critical | 2022-10-13 15:04 | 14.1556 | 0
| 70 | SDFI-916 | HIE-CM | 2022-09-29 13:02 | 9 | Blocker | 2022-09-30 15:02 | 1.0833 | 0
| 71 | SDFI-919 | PHR APP | 2022-09-29 14:20 | 9 | Blocker | 2022-10-14 12:54 | 14.9403 | 2
| 72 | SDFI-922 | ABHA ID | 2022-09-29 15:34 | 9 | Blocker | 2022-10-06 11:21 | 6.8243 | 0
| 73 | SDFI-931 | ABHA ID | 2022-09-29 17:58 | 9 | Major | 2022-11-11 09:51 | 42.6618 | 2
| 74 | SDFI-934 | PHR APP | 2022-09-30 10:19 | 9 | Blocker | 2022-10-26 13:12 | 26.1201 | 6
| 75 | SDFI-935 | PHR APP | 2022-09-30 10:34 | 9 | Blocker | 2022-10-26 13:52 | 26.1375 | 6
| 76 | SDFI-936 | HIE-CM | 2022-09-30 11:31 | 9 | Major | 2022-10-07 10:48 | 6.9701 | 0
| 77 | SDFI-938 | ABHA ID | 2022-09-30 13:43 | 9 | Blocker | Open | 142.4285 | 54
| 78 | SDFI-944 | HIE-CM | 2022-09-30 17:29 | 9 | Minor | 2022-10-10 13:28 | 9.8326 | 0
| 79 | SDFI-946 | PHR APP | 2022-09-30 17:59 | 9 | Blocker | 2022-10-06 13:13 | 5.8014 | 0
| 80 | SDFI-958 | PHR APP | 2022-10-03 11:34 | 10 | Major | 2022-10-06 14:32 | 3.1236 | 0
| 81 | SDFI-967 | HIE-CM | 2022-10-03 14:51 | 10 | Critical | 2022-10-03 15:48 | 0.039583 | 0
| 82 | SDFI-971 | ABHA ID | 2022-10-03 15:03 | 10 | Critical | 2022-11-07 14:46 | 34.9882 | 6
| 83 | SDFI-978 | HIE-CM | 2022-10-03 17:26 | 10 | Critical | 2022-10-10 12:54 | 6.8111 | 0
| 84 | SDFI-979 | HIE-CM | 2022-10-03 20:42 | 10 | Blocker | 2022-10-26 13:42 | 22.7083 | 6
| 85 | SDFI-980 | ABDM Website | 2022-10-04 10:21 | 10 | Critical | 2022-10-12 14:46 | 8.184 | 0
| 86 | SDFI-982 | ABDM Website | 2022-10-04 10:34 | 10 | Critical | 2022-10-12 14:45 | 8.1743 | 0
| 87 | SDFI-983 | PHR APP | 2022-10-04 13:18 | 10 | Blocker | 2022-10-25 11:09 | 20.9104 | 4
| 88 | SDFI-987 | HFR | 2022-10-04 17:12 | 10 | Major | 2022-10-26 21:48 | 22.1917 | 0
| 89 | SDFI-989 | PHR APP | 2022-10-06 12:59 | 10 | Blocker | 2022-10-07 14:24 | 1.059 | 0
| 90 | SDFI-990 | PHR APP | 2022-10-06 13:35 | 10 | Blocker | 2022-11-11 10:39 | 35.8778 | 10
| 91 | SDFI-991 | ABHA ID | 2022-10-06 13:59 | 10 | Blocker | 2022-11-04 15:19 | 29.0556 | 8
| 92 | SDFI-995 | ABHA ID | 2022-10-06 14:31 | 10 | Critical | 2022-11-03 18:02 | 28.1465 | 4
| 93 | SDFI-1002 | ABDM Website | 2022-10-06 16:22 | 10 | Major | 2022-10-07 16:35 | 1.009 | 0
| 94 | SDFI-1003 | PHR APP | 2022-10-06 16:58 | 10 | Blocker | Open | 136.2931 | 50
| 95 | SDFI-1006 | PHR APP | 2022-10-06 20:14 | 10 | Blocker | 2022-11-04 14:56 | 28.7792 | 8
| 96 | SDFI-1007 | ABHA ID | 2022-10-07 11:16 | 10 | Blocker | 2022-11-03 16:08 | 27.2028 | 8
| 97 | SDFI-1028 | PHR APP | 2022-10-10 12:22 | 10 | Blocker | 2022-10-26 13:06 | 16.0306 | 2
| 98 | SDFI-1059 | HIE-CM | 2022-10-11 11:54 | 10 | Critical | 2022-10-21 12:35 | 10.0285 | 0
| 99 | SDFI-1063 | ABHA ID | 2022-10-11 12:14 | 10 | Critical | Open | 131.4903 | 46
| 100 | SDFI-1064 | ABHA ID | 2022-10-12 09:55 | 10 | Blocker | 2022-11-03 16:30 | 22.2743 | 6
| 101 | SDFI-1071 | ABHA ID | 2022-10-12 12:34 | 10 | Major | 2022-11-03 17:58 | 22.225 | 0
| 102 | SDFI-1082 | ABHA ID | 2022-10-13 16:01 | 10 | Major | 2022-11-07 15:12 | 24.966 | 0
| 103 | SDFI-1084 | ABHA ID | 2022-10-13 16:14 | 10 | Critical | 2022-11-07 15:12 | 24.9569 | 2
| 104 | SDFI-1086 | ABHA ID | 2022-10-13 16:27 | 10 | Major | 2022-10-25 11:06 | 11.7771 | 0
| 105 | SDFI-1088 | ABHA ID | 2022-10-13 16:34 | 10 | Major | 2022-11-07 15:11 | 24.9424 | 0
| 106 | SDFI-1089 | HIE-CM | 2022-10-13 18:04 | 10 | Critical | Open | 129.2472 | 44
| 107 | SDFI-1105 | PHR APP | 2022-10-15 06:44 | 10 | Blocker | 2022-10-18 12:54 | 3.2569 | 0
| 108 | SDFI-1106 | PHR APP | 2022-10-15 06:52 | 10 | Blocker | 2022-10-26 14:24 | 11.3139 | 0
| 109 | SDFI-1107 | PHR APP | 2022-10-15 07:02 | 10 | Blocker | 2022-11-01 17:07 | 17.4201 | 4
| 110 | SDFI-1108 | PHR APP | 2022-10-15 07:49 | 10 | Blocker | 2022-10-31 12:13 | 16.1833 | 2
| 111 | SDFI-1109 | PHR Web | 2022-10-15 11:50 | 10 | Blocker | 2022-10-25 11:04 | 9.9681 | 0
| 112 | SDFI-1112 | PHR APP | 2022-10-15 15:18 | 10 | Blocker | 2022-10-26 17:04 | 11.0736 | 0
| 113 | SDFI-1113 | PHR APP | 2022-10-16 09:16 | 10 | Blocker | 2022-10-18 09:54 | 2.0264 | 0
| 114 | SDFI-1116 | ABHA ID | 2022-10-17 10:32 | 10 | Critical | 2022-10-25 11:04 | 8.0222 | 0
| 115 | SDFI-1117 | HIE-CM | 2022-10-17 11:27 | 10 | Critical | Open | 125.5229 | 44
| 116 | SDFI-1119 | ABHA ID | 2022-10-17 13:03 | 10 | Blocker | 2022-11-03 14:01 | 17.0403 | 4
| 117 | SDFI-1120 | ABHA ID | 2022-10-17 14:18 | 10 | Not Filled | 2022-11-11 09:55 | 24.8174 | NA
| 118 | SDFI-1123 | ABHA ID | 2022-10-17 16:30 | 10 | Not Filled | 2022-10-25 12:59 | 7.8535 | NA
| 119 | SDFI-1138 | EMR | 2022-10-18 13:49 | 10 | Not Filled | 2022-10-18 13:53 | 0.0027778 | NA
| 120 | SDFI-1139 | HFR | 2022-10-18 15:03 | 10 | Critical | 2022-10-28 09:57 | 9.7875 | 0
| 121 | SDFI-1143 | EMR | 2022-10-18 15:49 | 10 | Not Filled | 2022-10-25 13:04 | 6.8854 | NA
| 122 | SDFI-1144 | EMR | 2022-10-18 16:09 | 10 | Not Filled | 2022-10-25 12:42 | 6.8563 | NA
| 123 | SDFI-1146 | EMR | 2022-10-18 17:26 | 10 | Not Filled | 2022-10-25 14:11 | 6.8646 | NA
| 124 | SDFI-1147 | EMR | 2022-10-18 17:28 | 10 | Not Filled | 2022-10-25 12:24 | 6.7889 | NA
| 125 | SDFI-1172 | ABHA ID | 2022-10-20 15:49 | 10 | Major | 2022-10-25 16:55 | 5.0458 | 0
| 126 | SDFI-1178 | HPR | 2022-10-21 09:56 | 10 | Critical | 2022-11-11 10:02 | 21.0042 | 2
| 127 | SDFI-1179 | ABHA ID | 2022-10-21 12:03 | 10 | Not Filled | 2022-10-21 12:26 | 0.015972 | NA
| 128 | SDFI-1180 | ABHA ID | 2022-10-21 12:15 | 10 | Blocker | 2022-11-03 16:30 | 13.1771 | 2
| 129 | SDFI-1189 | ABHA ID | 2022-10-22 09:22 | 10 | Blocker | Open | 120.6097 | 44
| 130 | SDFI-1190 | HIE-CM | 2022-10-22 12:45 | 10 | Blocker | 2022-10-25 12:14 | 2.9785 | 0
| 131 | SDFI-1193 | HIE-CM | 2022-10-25 11:54 | 10 | Major | 2022-11-07 10:59 | 12.9618 | 0
| 132 | SDFI-1194 | HIE-CM | 2022-10-25 16:02 | 10 | Minor | 2022-11-01 16:59 | 7.0396 | 0
| 133 | SDFI-1196 | ABHA ID | 2022-10-25 19:38 | 10 | Blocker | 2022-11-09 11:32 | 14.6625 | 2
| 134 | SDFI-1209 | ABHA ID | 2022-10-27 15:11 | 10 | Major | Open | 115.3674 | 17
| 135 | SDFI-1213 | HIE-CM | 2022-10-28 10:43 | 10 | Critical | 2022-11-11 10:24 | 13.9868 | 0
| 136 | SDFI-1219 | ABHA ID | 2022-10-31 09:32 | 10 | Critical | 2022-11-04 15:29 | 4.2479 | 0
| 137 | SDFI-1224 | PHR APP | 2022-10-31 10:42 | 10 | Critical | 2022-11-01 10:43 | 1.0007 | 0
| 138 | SDFI-1229 | ABHA ID | 2022-10-31 14:17 | 10 | Major | 2022-11-04 12:47 | 3.9375 | 0
| 139 | SDFI-1239 | HIE-CM | 2022-10-31 19:03 | 10 | Blocker | 2022-11-03 11:46 | 2.6965 | 0
| 140 | SDFI-1241 | PHR APP | 2022-10-31 19:25 | 10 | Blocker | 2022-11-02 10:56 | 1.6465 | 0
| 141 | SDFI-1247 | ABHA ID | 2022-11-01 16:24 | 11 | Minor | 2022-11-03 17:56 | 2.0639 | 0
| 142 | SDFI-1249 | ABHA ID | 2022-11-01 17:19 | 11 | Major | Open | 110.2785 | 16
| 143 | SDFI-1272 | ABHA ID | 2022-11-02 12:53 | 11 | Blocker | 2022-11-07 15:55 | 5.1264 | 0
| 144 | SDFI-1274 | ABHA ID | 2022-11-02 12:58 | 11 | Critical | 2022-11-04 17:08 | 2.1736 | 0
| 145 | SDFI-1276 | ABHA ID | 2022-11-02 13:04 | 11 | Major | Open | 109.4556 | 15
| 146 | SDFI-1283 | HIE-CM | 2022-11-02 21:22 | 11 | Blocker | 2022-11-02 21:30 | 0.0055556 | 0
| 147 | SDFI-1297 | PHR Web | 2022-11-03 11:24 | 11 | Critical | 2022-11-09 10:50 | 5.9764 | 0
| 148 | SDFI-1304 | HIE-CM | 2022-11-03 12:28 | 11 | Blocker | 2022-11-03 12:54 | 0.018056 | 0
| 149 | SDFI-1307 | HIE-CM | 2022-11-03 13:06 | 11 | Critical | 2022-11-03 13:13 | 0.0048611 | 0
| 150 | SDFI-1318 | ABHA ID | 2022-11-04 14:53 | 11 | Minor | 2022-11-04 16:04 | 0.049306 | 0
| 151 | SDFI-1320 | ABHA ID | 2022-11-04 15:02 | 11 | Minor | 2022-11-04 15:06 | 0.0027778 | 0
| 152 | SDFI-1327 | HIE-CM | 2022-11-05 17:29 | 11 | Major | Open | 106.2715 | 15
| 153 | SDFI-1345 | ABHA ID | 2022-11-07 17:15 | 11 | Critical | Open | 104.2812 | 34
| 154 | SDFI-1346 | ABHA ID | 2022-11-08 07:45 | 11 | Blocker | 2022-11-08 12:38 | 0.20347 | 0
| 155 | SDFI-1348 | ABHA ID | 2022-11-08 12:20 | 11 | Major | 2022-11-08 13:25 | 0.045139 | 0
| 156 | SDFI-1352 | ABHA ID | 2022-11-08 13:18 | 11 | Critical | 2022-11-10 10:24 | 1.8792 | 0
| 157 | SDFI-1353 | ABHA ID | 2022-11-09 09:55 | 11 | Minor | 2022-11-10 10:24 | 1.0201 | 0
| 158 | SDFI-1354 | HIE-CM | 2022-11-09 10:30 | 11 | Blocker | 2022-11-10 10:56 | 1.0181 | 0
| 159 | SDFI-1359 | PHR Web | 2022-11-09 10:54 | 11 | Major | Open | 102.5458 | 14
| 160 | SDFI-1364 | HIE-CM | 2022-11-09 13:15 | 11 | Critical | 2022-11-11 11:25 | 1.9236 | 0
| 161 | SDFI-1367 | ABHA ID | 2022-11-09 14:05 | 11 | Blocker | Open | 102.4132 | 38
| 162 | SDFI-1381 | HIE-CM | 2022-11-10 10:49 | 11 | Major | Open | 101.5493 | 14
| 163 | SDFI-1390 | PHR APP | 2022-11-11 11:05 | 11 | Major | Open | 100.5382 | 14
| 164 | SDFI-1393 | HIE-CM | 2022-11-11 11:22 | 11 | Blocker | Open | 100.5264 | 36
| 165 | SDFI-1395 | ABHA ID | 2022-11-11 12:25 | 11 | Major | 2022-11-11 16:52 | 0.18542 | 0
Formulas:
Days Variance = IFERROR(DAYS([Resolution Date],[Created Date]), DAYS(TODAY(),[Created Date]))

## SLA-4
SLA 004- Defect count in Production environment
| Month | Current Month WAC | Baseline | Variance % | Calculation of Severity Level | Remarks | LD Points | Quarterly LD Points | Applicable LD | App Count in SLA-3
| Sep | 0.82 | 0 | 0 | 0 | Baseline | 0 | -9 | 0 | 8
| Oct | 0.67 | 0.82 | -18.2927 | -3.6585 | 0 is minimum cap | -4
| Nov | 0.5 | 0.67 | -25.3731 | -5.0746 | 0 is minimum cap | -5
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Every increase or decrease up to 5% from baseline results in Increases or decreases by 1. However, example mentions increase or decrease by 2.

## SLA-5
SLA 005- Upgrade of applications to support the (N-1) version of technology components
environment types | ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance
Production | GRIEVANCE PORTAL | OS | RHEL | 7.8 | 9 | OpenSource |  | No
|  | Platform | PHP | 7.4 | 8.1 | OpenSource |  | Yes
|  | Platform | HTML | 5 | 5 | Standard |  | Yes
|  | Platform | Bootstrap | 3.3 | 5 | OpenSource |  | No
|  | Platform | jQuery | 2.2.4 | 3.6.1 | OpenSource |  | Yes
|  | Platform | CSS | 3 | 3 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | No
|  | DB | MySQL | 5.7.34 | 5.8 | OpenSource |  | Yes
| DASHBOARD | OS | RHEL | 7.9 | 9 | OpenSource |  | No
|  | Platform | Java (JDK) | 1.8 | 1.9 | OpenSource |  | Yes
|  | Platform | Spring Boot | 2.5.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 5.1.3 | 5 | OpenSource |  | Yes
|  | Platform | Angular | 12.1.1 | 14 | OpenSource |  | No
|  | DB | PostgreSQL | 12.3 | 15 | OpenSource |  | No
| SANDBOX | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | React JS | 16.8 | 18.2.0 | OpenSource |  | No
|  | Platform | PHP | 7 | 8.1 | OpenSource |  | Yes
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 10.1.0 | 10.1.0 | OpenSource |  | No
| HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | Yes
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | Yes
|  | Platform | PHP (Cake PHP) | 7.3.28 | 8.1 | OpenSource |  | Yes
|  | Platform | HTML | 5 | 5 | OpenSource |  | Yes
|  | Platform | CSS | 3 | 3 | OpenSource |  | Yes
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | No
| ABDM WebSite | OS | RHEL | 7.7 | 9 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.0.0 | OpenSource |  | Yes
|  | Web Server | Node Server | 16.14.2 | 19.0.1 | OpenSource |  | No
|  | Platform | HTML | 5.0 | 5.0 | Standard |  | Yes
|  | DB | PostgreSQL | 14.4 | 15 | OpenSource |  | Yes
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | Yes
|  | Platform | Java | 8 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | No
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | No
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Java | 8 | 19 | OpenSource |  | No
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | No
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | Yes
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | Yes
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
| EMR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | Yes
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | No
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | No
| HFR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | Yes
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | No
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | No
| PHR App | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Eclipse | 21+ | 4.23 | OpenSource |  | No
|  | Application | PgAdmin | 4 | 4 | OpenSource |  | Yes
|  | Platform | Visual Studio Code | 1.6 | 1.73 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | Yes
|  | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Android Studio | 2021.3.1 | 2021.3.1 | OpenSource |  | Yes
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | No
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | Yes
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | Yes
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | Yes
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | Yes
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | No
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | Yes
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | No
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | No
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | Yes
|  | Platform | .NET | 3.1 | 4.8.1 | OpenSource |  | No
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | Yes
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | Yes
environment types | ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance
Beta-Stagging | GRIEVANCE PORTAL | OS | RHEL | 7.9 | 9 | OpenSource |  | No
|  | Platform | PHP | 7.4 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | Standard |  | YES
|  | Platform | Bootstrap | 4.3.1 | 5 | OpenSource |  | YES
|  | Platform | jQuery | 3.5.1 | 3.6.1 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
|  | DB | MySQL | 5.7.34 | 5.8 | OpenSource |  | YES
| SANDBOX | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | React JS | 16.8 | 18.2.0 | OpenSource |  | NO
|  | Platform | PHP | 7 | 8.1 | OpenSource |  | YES
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 10.1.0 | 10.1.0 | OpenSource |  | NO
| HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | YES
|  | Platform | PHP (Cake PHP) | 7.2.32 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
| ABDM WebSite | OS | RHEL | 7.7 | 9 | OpenSource |  | NO
|  | Platform | React JS | 17.0.2 | 18.0.0 | OpenSource |  | YES
|  | Web Server | Node Server | 16.14.2 | 19.0.1 | OpenSource |  | NO
|  | Platform | HTML | 5.0 | 5.0 | Standard |  | YES
|  | DB | PostgreSQL | 14.4 | 15 | OpenSource |  | YES
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.7.5 | 2.7.5 | OpenSource |  | YES
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | YES
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | NO
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | YES
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | YES
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | YES
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | YES
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | YES
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | NO
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | YES
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | No
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | No
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Rider IDE |  | 2022.2.3
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | YES
|  | Platform | .NET | 3.1 |  | OpenSource
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | YES
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | YES
environment types | ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance
Sandbox | HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | YES
|  | Platform | PHP (Cake PHP) | 7.2.32 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | NO
|  |  | KeyCloak |  | 20.0.0 | OpenSource | TCL manage
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource | TCL manage
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
| EMR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | YES
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | YES
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | NO
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | NO
| HFR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | YES
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | YES
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | NO
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | NO
| PHR App | DB | PostgreSQL | 13 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | Eclipse | 21+ | 4.23 | OpenSource |  | NO
|  | Application | PgAdmin | 4 | 4 | OpenSource |  | YES
|  | Platform | Visual Studio Code | 1.6 | 1.73 | OpenSource |  | NO
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Android Studio | 2021.3.1 | 2021.3.1 | OpenSource |  | YES
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | NO
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | YES
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | YES
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | YES
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | YES
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | YES
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | NO
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | YES
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | NO
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | NO
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | YES
|  | Platform | .NET | 3.1 | 4.8.1 | OpenSource |  | NO
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | YES
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | YES

## SLA-6
SLA 006- Mobilization of all selected ‘Core’ resources as per the timeline
| SI | Name | Onboarding Date | Title | Profile Deployment Date | Quarter Start Date | Deployment Gap | Applied Severity Level | Remarks
| 1 | Jitin Chugh | 2022-10-28 | Technical Director | 2022-03-04 | 2022-08-14 | 75 | 4 | Pramod Mankar exited on 13 Aug 2022.
| 2 | Sumit Gupta | 2022-03-04 | Project Manager | 2022-03-04 | 2022-08-14 | 0 | 0
| 3 | Abhishek Srivastava | 2022-05-02 | Enterprise Architect | 2022-03-04 | 2022-08-14 | 0 | 0
| 4 | Pankaj Narang | 2022-08-01 | Technology Lead | 2022-08-01 | 2022-08-14 | 0 | 0
| 5 | Sharfuddin | 2022-07-11 | Business Process Expert (BA) | 2022-03-04 | 2022-08-14 | 0 | 0
| 6 | Pranay Goswami | 2022-10-03 | UI designer and Usability Expert | 2022-03-04 | 2022-08-14 | 0 | 0 | Pranay Goswami replaced Nilesh Mahajan
| 7 | Rajan Agarwal | 2022-08-05 | IT Infra/Cloud Expert | 2022-08-05 | 2022-08-14 | 0 | 0
| 8 | Ankur Arora | 2022-09-26 | Security Expert | 2022-04-29 | 2022-08-14 | 0 | 0 | Ankur Arora replaced Abhishek Gupta
| 9 |  |  | Analytics Expert |  |  | 0 | 0
| 10 | Rahul Verma | 2022-03-04 | DevOps Expert | 2022-03-04 | 2022-08-14 | 0 | 0
| 11 |  |  | Agile Lead/ Scrum Master |  |  | 0 | 0
| 12 | Maneesh Sharma | 2022-03-04 | Contact Center Lead | 2022-03-04 | 2022-08-14 | 0 | 0

## SLA-7
SLA 007- Mobilization of 100% Other resources as per the timeline
| SI | O&M Resource(s) | Onboarding Date | Title | Planned Date | Target | Applied Severity Level | Remarks
| 1 | Siddharth Asthana | 2022-03-04 | Operations Manager | 2022-08-14 | 163 | 0
| 2 | Santosh Jagtap | 2022-03-04 | Sr. Developer | 2022-08-14 | 163 | 0
| 3 | Selva Ganesh/ Neelendra Singh | 2022-04-04 | Sr. Developer | 2022-08-14 | 132 | 0
| 4 | Govind Deshmukh | 2022-04-04 | Developer | 2022-08-14 | 132 | 0
| 5 | Praveen Gupta | 2022-03-04 | Developer | 2022-08-14 | 163 | 0
| 6 | Shubhanshu Shukla | 2022-05-23 | Developer | 2022-08-14 | 83 | 0
| 7 | Manish Kumar | 2022-06-01 | Developer | 2022-08-14 | 74 | 0
| 8 | Atik Mohammad | 2022-06-01 | Developer | 2022-08-14 | 74 | 0
| 9 | Suraj Singh Karki | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 10 | Kavitha HR | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 11 | Amir Safi | 2022-06-15 | Sr. Testing Engineer | 2022-08-14 | 60 | 0
| 12 | Rajesh Verma | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 13 | Puja Rani | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 14 | Mohd. Jawwad | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 15 | Murugan Nagarajan | 2022-09-09 | Developer | 2022-08-14 | -26 | 0 | Amey Naik replaced by Murugan Nagarajan. SLA NA
| 16 | Abhimanyu Bhattar | 2022-06-15 | Sr. Developer | 2022-08-14 | 60 | 0
| 17 | Sai Kumar Boyini | 2022-06-15 | Sr. Testing Engineer | 2022-08-14 | 60 | 0
| 18 | Sujit Koli | 2022-06-07 | Developer | 2022-08-14 | 68 | 0
| 19 | Rajeev Ranjan | 2022-06-15 | Developer | 2022-08-14 | 60 | 0
| 20 | Akshay Pal | 2022-06-10 | Helpdesk Agent | 2022-08-14 | 65 | 0
| 21 | Sunil Balram Yadav | 2022-06-15 | Helpdesk Agent | 2022-08-14 | 60 | 0
| 22 | Kumar Atik | 2022-06-06 | Database Administrator | 2022-08-14 | 69 | 0
| 23 | Arpit Jain | 2022-03-21 | Sr. Developer | 2022-08-14 | 146 | 0
| 24 | Shalini Namdeo | 2022-05-27 | Developer | 2022-08-14 | 79 | 0
| 25 | Sachin | 2022-07-19 | Developer | 2022-08-14 | 26 | 0
| 26 | Lata Gupta | 2022-07-19 | QA/QC Lead | 2022-08-14 | 26 | 0
| 27 | Naresh Banoth | 2022-04-04 | Developer | 2022-08-14 | 132 | 0
| 28 | Manish Kumar | 2022-08-17 | Developer (PHP) | 2022-08-14 | -3 | 0 | Shweta Dhodare replaced by Manish Kumar. SLA NA
| 29 | Bhavya L | 2022-08-22 | Developer | 2022-08-14 | -8 | 0 | New addition. SLA NA
| 30 | Krishna D Kulkarni | 2022-08-29 | Sr. Testing Engineer | 2022-08-14 | -15 | 0 | New addition. SLA NA
| 31 | IAVV Sireesha | 2022-08-29 | Sr. Testing Engineer | 2022-08-14 | -15 | 0 | New addition. SLA NA
| 32 | Ashish Gaharwar | 2022-10-31 | Operations Manager | 2022-08-14 | -78 | 0 | New addition. SLA NA
| SI | CIE Resource(s) | Onboarding Date | Title | Remarks
| 1 | Umesh P Shinde | 2022-09-23 | Sr. Developer | Deployment date not planned. SLA NA
| 2 | Deepak Singh | 2022-03-04 | Developer
| 3 | Ganapathy P | 2022-08-10 | Sr. Developer
| 4 | Nikhil Vora | 2022-09-15 | Sr. Developer
| 5 | Mihir Parekh | 2022-11-14 | Sr. Developer
| 6 | Arun H Pal | 2022-09-19 | Developer
| 7 | Priya Pandey | 2022-08-05 | Developer
| 8 | Narayanan Madaswamy | 2022-10-31 | Sr. Developer
| 9 | Atul Kumar Sharma | 2022-09-22 | Developer
Formulas:
Target = DAYS([Planned Date],[Onboarding Date])

## SLA-8
SLA 008- No. of Resource replacement in a Quarter (for ‘Core Resources’)
| SI | Title | Onboarded Resource | Exiting resource | Applied Severity Level
| 1 | Security Expert | Ankur Arora | Abhishek Gupta | 0
| 2 | Technical Director | Jitin chugh | Pramod Mankar | 0
| 3 | UI/ UX Expert | Pranay Goswami | Nilesh Mahajan | 0

## SLA-9
SLA 009- Number of Resource replacement in a Quarter for (Other O& M Resources’)
| SI | Profile | Application | Onboarded Resource | Exiting resource | Applied Severity Level
| 1 | Developer | PHR Web | Murugan Nagarajan | Amey Naik | 0
| 2 | Developer | HPID | Irfan | Puja Rani | 0
| 4 | Developer | Sandbox | Manish Kumar | Shweta Dhodare | 0
| 5 | Sr. Developer | HFR | Neelendra Singh | Selva Ganesh | 0
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## SLA-10
SLA 010- Minimum overlap period during resource replacement
| SI | Profile | Onboarded Resource | Onboarding Date | Exiting Resource | Exit Date | Applied Severity Level
| 1 | Developer | Murugan Nagarajan | 2022-09-09 | Amey Naik | 2022-09-23 | 0
| 2 | Developer | Irfan | 2022-10-28 | Puja Rani | 2022-11-11 | 0
| 4 | Developer | Manish Kumar | 2022-08-17 | Shweta Dhodare | 2022-08-31 | 0
| 5 | Sr. Developer | Neelendra Singh | 2022-10-06 | Selva Ganesh | 2022-11-01 | 0
Formulas:
Applied Severity Level = IF(DAYS([Exit Date],[Onboarding Date])<=10, 2,0)

## SLA-11
SLA 011- Minimum resource availability (All resources 8*5 support resources’)
Effective working days - 65
Core | SI | Resource(s) | Date of Onboarding | Profile | Leaves Taken | Effective Workng Days | Remarks
| 1 | Jitin Chugh/ Pramod Mankar | 2022-10-28 | Technical Director | 0 | 10
| 2 | Sumit Gupta | 2022-03-04 | Project Manager | 11 | 50
| 3 | Abhishek Srivastava | 2022-05-02 | Enterprise Architect | 3 | 58
| 4 | Pankaj Narang | 2022-08-01 | Technology Lead | 4 | 43
| 5 | Sharfuddin | 2022-07-11 | Business Process Expert (BA) | 3 | 58
| 6 | Pranay Goswami | 2022-10-03 | UI designer and Usability Expert | 4 | 21 | Pranay replaced Nilesh Mahajan who was positioned as UI Expert
| 7 | Rajan Agarwal | 2022-08-05 | IT Infra/Cloud Expert | 3 | 26
| 8 | Ankur Arora /Abhishek Gupta | 2022-09-26 | Security Expert | 3 | 56
| 9 |  | 2022-03-04 | Analytics Expert | 0 | 0 | Chaitali was positioned as Analyitcs Expert in Pune.
| 10 | Rahul Verma | 2022-03-04 | DevOps Expert | 2 | 58
| 11 |  | 2022-03-04 | Agile Lead/ Scrum Master | 0 | 0 | Prasanna was positioned as Agile/ Scrum Lead
| 12 | Maneesh Sharma | 2022-03-04 | Contact Center Lead | 6 | 57
O&M | SI | Resource(s) | Date of Onboarding | Profile | Leaves Taken | Effective Workng Days | Remarks
| 1 | Siddharth Asthana | 2022-03-04 | Operations Manager | 1 | 60
| 2 | Santosh Jagtap | 2022-03-04 | Sr. Developer | 2 | 60
| 3 | Selva Ganesh/ Neelendra Singh | 2022-04-04 | Sr. Developer | 1 | 60
| 4 | Govind Deshmukh | 2022-04-04 | Developer | 5 | 56
| 5 | Praveen Gupta | 2022-03-04 | Developer | 3 | 60
| 6 | Shubhanshu Shukla | 2022-05-23 | Developer | 0 | 60
| 7 | Manish Kumar | 2022-06-01 | Developer | 0 | 60
| 8 | Atik Mohammad | 2022-06-01 | Developer | 1 | 60
| 9 | Suraj Singh Karki | 2022-06-15 | Developer | 1 | 60
| 10 | Kavitha HR | 2022-06-15 | Developer | 2 | 59
| 11 | Amir Saifi | 2022-06-15 | Sr. Testing Engineer | 5 | 57
| 12 | Rajesh Verma | 2022-06-15 | Developer | 0 | 60
| 13 | Puja Rani/ Irfan | 2022-06-15 | Developer | 0 | 60
| 14 | Mohd. Jawwad | 2022-06-15 | Developer | 2 | 60
| 15 | Murugan Nagarajan | 2022-09-09 | Developer | 1 | 60
| 16 | Abhimanyu Bhattar | 2022-06-15 | Sr. Developer | 14 | 49
| 17 | Sai Kumar Boyini | 2022-06-15 | Sr. Testing Engineer | 0 | 60
| 18 | Sujit Koli | 2022-06-07 | Developer | 5 | 58
| 19 | Rajeev Ranjan | 2022-06-15 | Developer | 0 | 60
| 20 | Akshay Pal | 2022-06-10 | Helpdesk Agent | 0 | 60
| 21 | Sunil Balram Yadav | 2022-06-15 | Helpdesk Agent | 0 | 60
| 22 | Kumar Atik | 2022-06-06 | Database Administrator | 3 | 60
| 23 | Arpit Jain | 2022-03-21 | Sr. Developer | 0 | 60
| 24 | Shalini Namdeo | 2022-05-27 | Developer | 2 | 60
| 25 | Sachin | 2022-07-19 | Developer | 0 | 60
| 26 | Lata Gupta | 2022-07-19 | QA/QC Lead | 3 | 60
| 27 | Naresh Banoth | 2022-04-04 | Developer | 10 | 52
| 28 | Manish Kumar | 2022-08-17 | Developer (PHP) | 0 | 60
| 29 | Bhavya L | 2022-08-22 | Developer | 2 | 49
| 30 | Krishna D Kulkarni | 2022-08-29 | Sr. Testing Engineer | 2 | 49
| 31 | IAVV Sireesha | 2022-08-29 | Sr. Testing Engineer | 4 | 48
| 32 | Ashish Gaharwar | 2022-10-31 | Operations Manager | 0 | 10
CIE | SI | Resource(s) | Date of Onboarding | Profile | Leaves Taken | Effective Workng Days | Remarks
| 1 | Nikhil Vora | 15-09-22 | Developer | 4 | 36
| 2 | Atul Kumar Sharma | 22-09-22 | Developer | 0 | 34
| 3 | Umesh P Shinde | 23-09-22 | Developer | 0 | 33
| 4 | Arun H Pal | 19-09-22 | Developer | 3 | 36
| 5 | Priya Pandey | 2022-05-08 | Developer | 5 | 47
| 6 | Ganapathy P | 2022-10-08 | Developer | 1 | 49
| 7 | Deepak Singh | 2022-04-03 | Developer | 5 | 57
| 8 | Narayanan Madaswamy | 2022-10-31 | Sr. Developer | 0 | 10

## SLA-12
SLA 012- Minimum resource availability (‘24*7 support resources’)
24x7 support resources not deployed in project

## SLA-13
SLA 013- Application uptime
Target and Applied Severity Level will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications.

## SLA-14
SLA 014- Application Performance
Target and Applied Severity Level will be decided mutually by the NHA and the MSP, at the end of the Design & Development Phase after benchmarking of existing applications.

## SLA-15
SLA 015- Application Incident resolution
Target and Applied Severity Level for P1, P2, P3 and P4 incidents will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications.
Sr. No. | FY | Month | Date (MM/DD/YYYY) | IN NO. | Issue Type | Application impacted | Category | Severity | Notified Time | Time stamp for allocation to L2 Technician | Response Time | Response Time SLA Met(Y / N / NA*) | Action taken | Closure date (MM/DD/YYYY) | Closure time | Resolution Time
1 | 2022-23 | September | 2022-09-12 | IN00009 | HIE-CM Sandbox application is giving the constant error where HIE-CM is unable to connect Health-Id. | HIECM | P3 | Major | 11:56 | 12:21 | 25 mins | Yes | Resolved | 2022-09-13 | 13:15 | 25 Hours
2 | 2022-23 | September | 2022-09-15 | IN00010 | HIE CM Down in Production | HIECM | P1 | Blocker | 21:00 | 21:00 | 1 mins | Yes | Resolved | 2022-09-16 | 2:00 | 5 hours
3 | 2022-23 | September | 2022-09-15 | IN00011 | Unble to connect to any of the HPR Server | HPR | P2 | Critical | 20:09 | 20:09 | 1 mins | Yes | Resolved | 2022-09-16 | 6:00 | 10 Hours
4 | 2022-23 | September | 2022-09-24 | IN00012 | Key Clock Issue - HIECM | HIECM | P1 | Blocker | 10:00 | 12:00 | 2 hours | No | Resolved | 2022-09-24 | 17:00 | 7 Hours
5 | 2022-23 | September | 2022-09-24 | IN00013 | EMR - API NOT CONNECTING | EMR | P2 | Critical | 10:00 | 12:00 | 2 hours | Yes | Resolved | 2022-09-24 | 17:00 | 7 Hours
6 | 2022-23 | September | 2022-09-29 | IN00014 | ABDM Dashboard Issue | Dashboard | P2 | Critical | 12:02 | 12:30 | 28 mins | Yes | Resolved | 2022-09-29 | 15:59 | 3.5 Hours
7 | 2022-23 | October | 2022-10-04 | IN00015 | ABDM Website Issue | ABDM Website | P1 | Blocker | 13:13 | 13:19 | 6 mins | Yes | Resolved | 2022-10-04 | 15:29 | 2.1 Hrs
8 | 2022-23 | October | 2022-10-07 | IN00016 | HID (ABHA) NDHM & ABDM PROD OTP issue | HID (ABHA) | P2 | Critical | 19:50 | 20:26 | 36 mins | Yes | Resolved | 2022-10-08 | 14:00 | 17.34 Hours
9 | 2022-23 | October | 2022-10-12 | IN00017 | Dashboard DB error | Dashboard | P2 | Critical | 7:30 | 8:26 | 56 mins | Yes | Resolved | 2022-10-12 | 9:00 | 1.5 hours
10 | 2022-23 | October | 2022-10-22 | IN00018 | Users unable to submit OTP in ABHA | Abha APP | P2 | Critical | 9:00 | 9:30 | 30 mins | Yes | Resolved | 2022-10-22 | 14:00 | 4.5 Hours
11 | 2022-23 | October | 2022-10-23 | IN00019 | Users unable to create PHR address | Abha APP | P2 | Critical | 10:00 | 10:30 | 30 mins | Yes | Resolved | 2022-10-23 | 16:00 | 5.5 Hours
12 | 2022-23 | October | 2022-10-26 | IN00020 | HPR Sandbox stopped working | HPR | P2 | Critical | 16:19 | 16:22 | 3 mins | Yes | Resolved | 2022-10-26 | 16:51 | 0.29 Hours
13 | 2022-23 | October | 2022-10-28 | IN00021 | Slowness Issue due to Firewall problem. Was resolved on day 1 but issue reoccured due to Migration activity of TCL pertaining to Firewall | Firewall issue which affected all applications | P2 | Critical | 14:50 | 15:00 | 10 Mins | Yes | Resolved | 2022-10-30 | 23:00 | 57.67 Hours
14 | 2022-23 | October | 2022-10-28 | IN00022 | ABDM Website Down | ABDM Website | P1 | Blocker | 12:31 | 12:36 | 5 mins | Yes | Resolved | 2022-10-28 | 13:03 | 32 Mins
15 | 2022-23 | October | 2022-10-25 | IN00023 | issues with PAAS services | Overall Application | P1 | Blocker | 22:20 | 22:50 | 30 mins | Yes | Resolved | 2022-10-26 | 12:39 | 1 Hour 50 Mins
16 | 2022-23 | November | 2022-11-04 | IN00024 | Gateway DB Connection issue | HIECM | P3 | Major | 11:47 | 12:00 | 13 Mins | Yes | Resolved | 2022-11-04 | 11:05 | 47 hours 42 mins
17 | 2022-23 | November | 2022-11-09 | IN00025 | PG Pool down | Database | P1 | Blocker | 14:30 | 14:32 | 2 Min | Yes | Resolved | 2022-10-26 | 15:15 | 45 mins