## SLA Calculation
SLA No. | SLA Description | Baseline | Target | Severity Level | Actual Deployment | Severity Level Applied | Penalty Points | Applicable Penalty on Planned Payment Cycle
SLA-001 | Submission of all the Deliverables | <=X (where X is targeted date of deliverable as per Table-B) | <=X | 0 | Refer tab SLA-1 | 0
|  |  | >X and <=X+7 days | 1
|  |  | >X+7 days and <=X+14 days | 2
|  |  | >X+14 days and <=X+21 days | 3
|  |  | >X+21 days | 4
SLA-002 | Defect count in UAT environment | <= baseline | <= baseline | 0 | Refer tab SLA-2 | -50
|  |  | Every increase or decrease up to 5% from baseline. | Increases or decreases by 1
SLA-003 | TAT for defects in Production environment | Blocker | ((<= 7 days (for complexity = 'low or moderate' or <=15days (for complexity = 'High' AND (workaround within 8 hours)) | 0 | Refer tab SLA-3 | -36
|  |  | ((Workaround not within 8 hours) or (Every additional 5 days for fixing defect)) | Increases by 2
|  | Critical | ((<= 15days (for complexity = 'low or moderate' or <=30days (for complexity = 'High' AND (workaround within 8 hours)) | 0
|  |  | ((Workaround not within 24 hours) or (Every additional 5 days for fixing defect)) | Increases by 2
|  | Major | ((<= 30days (for complexity = 'low or moderate' or <=45days (for complexity = 'High' AND (workaround within 8 hours)) | 0
|  |  | ((Workaround not within 24 hours) or (Every additional 5 days for fixing defect)) | Increases by 1
SLA-004 | Defect count in Production environment | <= baseline | <= baseline | 0 | Refer tab SLA-4 | -1
|  |  | Every increase or decrease up to 5% from baseline. | Increases or decreases by 1
SLA-005 | Upgrade of applications to support the (N-1) version of technology components | 100% completion, or the NHA does not approve upgrade of any technology components in the Year | 100% completion, or the NHA does not approve upgrade of any technology components in the Year | 0 | Refer tab SLA-5 | 2
|  |  | >=70% to <100% | 1
|  |  | <70% | 2
SLA-006 | Mobilization of all selected ‘Core’ resources as per the timeline | Mobilization of all resources within 15 days of contract signing | <15 Days | 0 | >30 Days (Refer tab Q3 Core Team) | -14
|  |  | >15 to 30 Days | 2
|  |  | >30 Days | 4
SLA-007 | Mobilization of 100% other resources as per timeline | Mobilization of all resources within 15 days of contract signing | <15 Days | 0 | Resources deployed | -84
|  |  | >15 to 30 Days | 2
|  |  | >30 Days | 4
SLA-008 | No. of Resource replacement in a Quarter (for ‘Core Resources’) | Up to ‘1’ replacement | Up to ‘1’ replacement | 0 | Refer tab SLA-8 | 2
|  |  | Every increase of ‘1’ replacement | Increases by 2
SLA-009 | No. of Resource replacement in a Quarter (for Other O& M Resources) | Up to ‘3’ replacement | Up to ‘3’ replacement | 0 | Refer tab SLA-9 | 0
|  |  | Every increase of ‘1’ replacement | Increases by 1
SLA-010 | Minimum overlap period during resource replacement | Overlap period >=2 business weeks | Overlap period >=2 business weeks | 0 | Refer tab SLA-10 | 0
|  |  | Overlap period < 2 business weeks | Increases by 1
SLA-011 | Minimum resource availability | Monthly availability for each project resource (except designated 24*7 support resources), including applicable leaves and NHA holidays | >= 16 business days and >=144 hours 0 per month. | 0 | Refer tab Q3 Core Team and Q3 O&M
|  |  | Between 12 to 16 business days and 108 to 144 hours per month | 2
|  |  | < 12 business days and < 108 hours | 4
SLA-012 | Minimum resource availability (‘24*7 support resources’) | Monthly availability, for Support resource | Monthly availability: 100% | 0 | Refer tab SLA-12
|  |  | Monthly availability: between 95% to 100% | 2
|  |  | Monthly availability: <= 95% | 4
SLA-013 | Application uptime | 99.95% | Target and Applied Severity Level will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications. |  | Refer SLA-13
SLA-014 | Application Performance |  | Target and Applied Severity Level will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications. |  | Refer SLA-14
SLA-015 | Application Incident Resolution |  | Target and Applied Severity Level for P1, P2, P3 and P4 incidents will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications. |  | Refer SLA-15
Overall Penalty %age | [7 empty] | 0%
Actual Calculated Penalty | [7 empty] | #REF!
Penalty as per 10% capping | [7 empty] | #REF!

## Holiday Calendar
|  |  | Start Date | End Date | Working Days
Holiday | Occasion | M1 | 2022-11-14 | 2022-12-13 | 22
2022-11-08 | Guru Nanak's Birthday | M2 | 2022-12-14 | 2023-01-13 | 23
2023-01-26 | Republic Day | M3 | 2023-01-14 | 2023-02-13 | 20
Formulas:
Working Days = NETWORKDAYS([Start Date],[End Date],Table2[Holiday])

## List (hidden)
Attendance Days | SLA Category
0 | A
1 | A
2 | A
3 | A
4 | A
5 | A
6 | A
7 | A
8 | A
9 | A
10 | A
11 | A
12 | B
13 | B
14 | B
15 | B
16 | C
17 | C
18 | C
19 | C
20 | C
21 | C
22 | C
23 | C
24 | C
25 | C
26 | C
27 | C
28 | C
29 | C
30 | C
31 | C

## Non-Core Planned Resources
S.No. | Technical Contact | Role | Experience
1 | Umesh P Shinde | Sr. Developer | 10
2 | Manish17 Kumar | Developer | 6
3 | Govind Deshmukh | Developer | 5
4 | Deepak Singh | Sr. Testing Engineer | 5
5 | Shubhanshu Shukla | Developer | 5
6 | Atik Mohammad | Developer | 5
7 | Ganapathy P | Sr. Developer | 11
8 | Nikhil Vora | Sr. Developer | 12
9 | Suraj Karki | Developer | 9
10 | Dhawal Mehta | Developer | 5.9
11 | Abhimanyu Bhattar | Sr. Developer | 10
12 | Sai Kumar Boyini | Sr. Testing Engineer | 5.5
13 | Murugan Nagarajan | Sr. Developer | 11
14 | Amir Safi | Sr. Testing Engineer | 7.6
15 | Arun H Pal | Developer | 5
16 | Rajesh Verma | Developer | 7.2
17 | Pooja Rani/ Irfan | Developer | 5.1
18 | Mohd. Jawwad/ Karthick | Developer | 7
19 | Priya Pandey | Developer | 5
20 | Naresh Banoth | Developer | 3
21 | Manish16 Kumar | Developer | 5
22 | Narayanan Madaswamy | Sr. Developer | 11
23 | Santosh Jagtap | Sr. Developer | 12
24 | Bhavya L. | Developer | 6
25 | Sachin | Developer | 5
26 | Neelendra Pratap Singh | Developer | 5
27 | Atul Kumar Sharma | Developer | 5
28 | Sujit Koli | Developer | 6
29 | Praveen Gupta | Developer | 6
30 | Akshay Pal | Helpdesk Agent | 3
31 | Sunil Balaram Yadav | Helpdesk Agent | 3
32 | Lata Gupta | QA/QC Lead | 7
33 | IAAV Sireesha | Sr. Testing Engineer | 6
34 | KrishnaD Kulkarni | Sr. Testing Engineer | 7
35 | Rajeev Ranjan | Developer | 6.5
36 | Kumar Atik | Database Administrator | 7
37 | Arpit Jain | Sr. Developer | 10
38 | Shalini Namdeo | Sr. Developer | 9
39 | Siddharth Asthana | Operations Manager | 17
40 | Ashish Gaharwar | Operations Manager | 15
41 | Anuj sharma | Developer | 6

## SLA-1
SLA 001- Submission of all the Deliverables (Deliverables related to Transition, Design and Development and O& M )
| SI | Deliverable | Track | Quarter | Contractual Date | Submission Date | SLA Calculation | Applied Severity level | Approval Date
| 1 | Service level compliance reports generated from SLA Monitoring Tool. | C2 | 4 | 2023-02-15 | 2023-02-20 | 5 | 0
| 2 | Following deliverables are required on regular basis: • Updated system design documents, specifications • Latest source code, application deployment files, configuration files for entire solution • Updated user manuals, administration manuals, training manuals etc. • Software change logs etc. • Adherence to the proposed Transition and Data Migration Plan • Help Desk/ Contact Center Status Report • Sandbox Integration Report • WASA Certification Report | C2 | 4 | 2023-02-15 | 2023-02-15 | 0 | 0

## SLA-2
SLA 002- Defect count in UAT environment
No UAT environment defined in existing application landscape.
| Sr No. | Ticket ID | Blocks | Created Date | Month | Severity | Resolution Date | Days Variance | Applied Severity Level | Points
| 1 | DRGREG-1277 | DRGREG | 2023-02-03 11:47 | 2 | Critical | 2023-02-06 16:40 | 3.2035 | 0 | -2
| 2 | DRGREG-1276 | DRGREG | 2023-02-03 11:46 | 2 | Critical | 2023-02-06 14:32 | 3.1153 | 0 | -2
| 3 | DRGREG-1275 | DRGREG | 2023-02-03 11:43 | 2 | Major | 2023-02-08 21:20 | 5.4007 | 0 | -2
| 4 | DRGREG-1274 | DRGREG | 2023-02-03 11:42 | 2 | Critical | 2023-02-07 11:51 | 4.0062 | 0 | -2
| 5 | DRGREG-1273 | DRGREG | 2023-02-03 11:41 | 2 | Major | 2023-02-06 16:17 | 3.1917 | 0 | -2
| 6 | DRGREG-1272 | DRGREG | 2023-02-03 11:36 | 2 | Major | 2023-02-07 12:43 | 4.0465 | 0 | -2
| 7 | DRGREG-1269 | DRGREG | 2023-02-03 11:34 | 2 | Major | 2023-02-06 16:18 | 3.1972 | 0 | -2
| 8 | DRGREG-1268 | DRGREG | 2023-02-03 11:33 | 2 | Major | 2023-02-07 10:11 | 3.9431 | 0 | -2
| 9 | DRGREG-1267 | DRGREG | 2023-02-03 11:32 | 2 | Minor | 2023-02-06 16:20 | 3.2 | 0 | -2
| 10 | DRGREG-1266 | DRGREG | 2023-02-03 11:29 | 2 | Major | 2023-02-06 15:13 | 3.1556 | 0 | -2
| 11 | DRGREG-1265 | DRGREG | 2023-02-03 11:27 | 2 | Major | 2023-02-06 15:49 | 3.1819 | 0 | -2
| 12 | DRGREG-1264 | DRGREG | 2023-02-03 11:23 | 2 | Major | 2023-02-06 11:10 | 2.991 | 0 | -2
| 13 | DRGREG-1262 | DRGREG | 2023-02-03 11:16 | 2 | Major | 2023-02-06 16:23 | 3.2132 | 0 | -2
| 14 | DRGREG-1238 | DRGREG | 2023-02-01 13:47 | 2 | Major | 2023-02-09 15:50 | 8.0854 | 0 | -2
| 15 | DRGREG-1237 | DRGREG | 2023-02-01 13:46 | 2 | Major | 2023-02-10 12:58 | 8.9667 | 0 | -2
| 16 | DRGREG-1236 | DRGREG | 2023-02-01 13:45 | 2 | Major | 2023-02-06 16:25 | 5.1111 | 0 | -2
| 17 | DRGREG-1235 | DRGREG | 2023-02-01 13:39 | 2 | Major | 2023-02-08 21:48 | 7.3396 | 0 | -2
| 18 | DRGREG-1233 | DRGREG | 2023-02-01 12:53 | 2 | Major | 2023-02-05 20:35 | 4.3208 | 0 | -2
| 19 | DRGREG-1232 | DRGREG | 2023-02-01 12:52 | 2 | Major | 2023-02-06 16:29 | 5.1507 | 0 | -2
| 20 | DRGREG-1231 | DRGREG | 2023-02-01 12:48 | 2 | Major | 2023-02-06 16:32 | 5.1556 | 0 | -2
| 21 | DRGREG-1230 | DRGREG | 2023-02-01 12:10 | 2 | Major | 2023-02-02 11:35 | 0.97569 | 0 | -2
| 22 | DRGREG-1228 | DRGREG | 2023-02-01 11:17 | 2 | Major | 2023-02-07 10:11 | 5.9542 | 0 | -2
| 23 | DRGREG-1227 | DRGREG | 2023-02-01 11:16 | 2 | Major | 2023-02-05 21:20 | 4.4194 | 0 | -2
| 24 | DRGREG-1211 | DRGREG | 2023-01-27 21:45 | 1 | Major | 2023-02-06 16:36 | 9.7854 | 0 | -2
| 25 | DRGREG-1204 | DRGREG | 2023-01-27 14:53 | 1 | Major | 2023-02-06 16:52 | 10.0826 | 0 | -2
Formulas:
Days Variance = IFERROR(DAYS([Resolution Date],[Created Date]), DAYS(TODAY(),[Created Date]))

## SLA-3
Raised by NHA not internal ticktes
SLA 003- TAT for defects in Production environment
[11 empty] | In this Quarter (Effective date for SLA: PM1 approval date) |  |  |  |  | Public Holiday
| Sr No. | Ticket ID | Blocks | Created Date | Month | Severity | Resolution Date | Days Variance | Applied Severity Level | Points |  | Blocker | Critical | Major | Minor | 2022-07-10
| 1 | SDFI-2663 | PHR APP | 2023-02-13 10:15 | 2 | Major | 2023-02-14 11:26 | 1.0493 | 0 | -2 | Aug | NA | NA | NA | NA | 2022-08-09
| 2 | SDFI-2649 | HIE-CM | 2023-02-09 21:20 | 2 | Major | 2023-02-13 15:55 | 3.7743 | 0 | -2 | Sep |  |  |  |  | 2022-08-15
| 3 | SDFI-2617 | ABHA ID | 2023-02-08 14:21 | 2 | Minor | 2023-02-13 12:52 | 4.9382 | 0 | -2 | Oct |  |  |  |  | 2022-08-19
| 4 | SDFI-2606 | HIE-CM | 2023-02-08 09:55 | 2 | Critical | 2023-02-15 10:02 | 7.0049 | 0 | -2 | Nov | 24 | 17 | 11 | 1 | 2022-10-02
| 5 | SDFI-2601 | HIE-CM | 2023-02-07 15:26 | 2 | Blocker | 2023-02-08 10:18 | 0.78611 | 0 | -2 | Dec | 14 | 8 | 3 | 2 | 2022-10-05
| 6 | SDFI-2595 | ABHA ID | 2023-02-07 09:55 | 2 | Blocker | 2023-02-07 15:46 | 0.24375 | 0 | -2 | Jan | 8 | 14 | 6 | 1 | 2022-10-09
| 7 | SDFI-2592 | HIE-CM | 2023-02-06 18:09 | 2 | Critical | 2023-02-13 10:25 | 6.6778 | 0 | -2 | Feb | 7 | 4 | 2 | 1
| 8 | SDFI-2574 | HFR | 2023-02-04 10:08 | 2 | Critical | 2023-02-08 13:57 | 4.159 | 0 | -2 | Total | 33 | 32 | 21 | 5 | 2022-10-24
| 9 | SDFI-2543 | HIE-CM | 2023-02-02 18:24 | 2 | Blocker | 2023-02-07 15:29 | 4.8785 | 0 | -2 | [5 empty] | 2022-11-02
| 10 | SDFI-2540 | ABHA ID | 2023-02-02 17:02 | 2 | Critical | 2023-02-07 15:49 | 4.9493 | 0 | -2 | [5 empty] | 2022-11-08
| 11 | SDFI-2528 | HIE-CM | 2023-02-02 10:58 | 2 | Blocker | 2023-02-06 12:20 | 4.0569 | 0 | -2 | [5 empty] | 2022-12-25
| 12 | SDFI-2527 | ABHA ID | 2023-02-02 10:03 | 2 | Blocker | 2023-02-08 10:55 | 6.0361 | 0 | -2 | [5 empty] | 2022-01-26
| 13 | SDFI-2507 | ABHA ID | 2023-02-01 11:22 | 2 | Blocker | 2023-02-02 09:59 | 0.94236 | 0 | -2
| 14 | SDFI-2506 | HIE-CM | 2023-02-01 10:34 | 2 | Blocker | 2023-02-06 18:08 | 5.3153 | 0 | -2
| 15 | SDFI-2470 | ABHA ID | 2023-01-27 10:57 | 1 | Critical | 2023-02-10 11:39 | 14.0292 | 0 | -2
| 16 | SDFI-2467 | HIE-CM | 2023-01-27 10:07 | 1 | Critical | 2023-02-13 17:30 | 17.3076 | 0 | -2
| 17 | SDFI-2451 | ABHA ID | 2023-01-24 17:09 | 1 | Blocker | 2023-02-01 13:19 | 7.8403 | 0 | -2
| 18 | SDFI-2433 | PHR APP | 2023-01-24 11:00 | 1 | Critical | 2023-02-01 10:12 | 7.9667 | 0 | -2
| 19 | SDFI-2425 | PHR APP | 2023-01-23 15:33 | 1 | Critical | 2023-02-01 11:55 | 8.8486 | 0 | -2
| 20 | SDFI-2418 | HIE-CM | 2023-01-21 21:17 | 1 | Blocker | 2023-02-06 12:22 | 15.6285 | 2 | 4
| 21 | SDFI-2417 | HIE-CM | 2023-01-21 21:15 | 1 | Major | 2023-02-07 11:31 | 16.5944 | 0 | -2
| 22 | SDFI-2415 | HIE-CM | 2023-01-21 20:57 | 1 | Major | 2023-02-13 09:45 | 22.5333 | 0 | -2
| 23 | SDFI-2413 | HIE-CM | 2023-01-21 18:58 | 1 | Critical | 2023-01-25 15:40 | 3.8625 | 0 | -2
| 24 | SDFI-2410 | HIE-CM | 2023-01-20 15:59 | 1 | Minor | 2023-01-20 16:00 | 0.00069444 | 0 | -2
| 25 | SDFI-2404 | HIE-CM | 2023-01-20 09:41 | 1 | Major | 2023-02-07 11:26 | 18.0729 | 0 | -2
| 26 | SDFI-2373 | ABHA ID | 2023-01-18 09:54 | 1 | Blocker | 2023-02-03 12:21 | 16.1021 | 2 | 4
| 27 | SDFI-2372 | HIE-CM | 2023-01-18 09:51 | 1 | Blocker | 2023-01-18 16:58 | 0.29653 | 0 | -2
| 28 | SDFI-2347 | ABHA ID | 2023-01-17 15:07 | 1 | Critical | 2023-02-01 16:46 | 15.0687 | 0 | -2
| 29 | SDFI-2341 | ABHA ID | 2023-01-17 10:27 | 1 | Major | 2023-01-23 12:23 | 6.0806 | 0 | -2
| 30 | SDFI-2340 | HIE-CM | 2023-01-17 10:06 | 1 | Critical | 2023-01-19 16:27 | 2.2646 | 0 | -2
| 31 | SDFI-2329 | ABHA ID | 2023-01-16 14:25 | 1 | Critical | 2023-01-16 15:39 | 0.051389 | 0 | -2
| 32 | SDFI-2325 | PHR APP | 2023-01-16 11:32 | 1 | Critical | 2023-01-27 11:38 | 11.0042 | 0 | -2
| 33 | SDFI-2306 | HIE-CM | 2023-01-13 17:01 | 1 | Critical | 2023-01-21 22:18 | 8.2201 | 0 | -2
| 34 | SDFI-2280 | ABHA ID | 2023-01-12 19:09 | 1 | Major | 2023-02-07 11:30 | 25.6813 | 0 | -2
| 35 | SDFI-2270 | HIE-CM | 2023-01-12 12:49 | 1 | Critical | 2023-01-31 15:24 | 19.1076 | 0 | -2
| 36 | SDFI-2250 | ABHA ID | 2023-01-11 13:12 | 1 | Blocker | 2023-01-11 19:53 | 0.27847 | 0 | -2
| 37 | SDFI-2225 | HIE-CM | 2023-01-10 09:56 | 1 | Major | 2023-02-10 10:30 | 31.0236 | 0 | -2
| 38 | SDFI-2190 | HIE-CM | 2023-01-09 11:32 | 1 | Critical | 2023-02-15 09:23 | 36.9104 | 8 | 8
| 39 | SDFI-2184 | ABHA ID | 2023-01-09 10:27 | 1 | Blocker | 2023-01-09 11:11 | 0.030556 | 0 | -2
| 40 | SDFI-2132 | PHR APP | 2023-01-04 10:58 | 1 | Blocker | 2023-02-01 12:01 | 28.0438 | 8 | 8
| 41 | SDFI-2122 | PHR APP | 2023-01-03 12:01 | 1 | Critical | 2023-01-27 11:19 | 23.9708 | 2 | 4
| 42 | SDFI-2110 | HFR | 2023-01-02 11:12 | 1 | Critical | 2023-01-03 11:50 | 1.0264 | 0 | -2
| 43 | SDFI-2109 | HIE-CM | 2023-01-01 10:19 | 1 | Blocker | 2023-01-06 11:15 | 5.0389 | 0 | -2
| 44 | SDFI-2092 | PHR APP | 2022-12-29 18:27 | 12 | Blocker | 2023-01-02 12:22 | 3.7465 | 0 | -2
| 45 | SDFI-2087 | HIE-CM | 2022-12-29 16:10 | 12 | Critical | 2023-02-01 13:01 | 33.8687 | 6 | 8
| 46 | SDFI-2086 | ABHA ID | 2022-12-29 15:06 | 12 | Critical | 2023-01-10 14:09 | 11.9604 | 0 | -2
| 47 | SDFI-2064 | PHR Web | 2022-12-28 15:09 | 12 | Blocker | 2023-01-03 11:57 | 5.8667 | 0 | -2
| 48 | SDFI-2005 | PHR Web | 2022-12-23 11:18 | 12 | Blocker | 2022-12-26 12:57 | 3.0688 | 0 | -2
| 49 | SDFI-1977 | HIE-CM | 2022-12-22 13:19 | 12 | Blocker | 2022-12-23 15:51 | 1.1056 | 0 | -2
| 50 | SDFI-1967 | HIE-CM | 2022-12-22 11:34 | 12 | Critical | 2022-12-22 17:38 | 0.25278 | 0 | -2
| 51 | SDFI-1906 | ABHA ID | 2022-12-19 11:57 | 12 | Critical | 2023-01-03 15:18 | 15.1396 | 0 | -2
| 52 | SDFI-1897 | PHR APP | 2022-12-19 09:53 | 12 | Blocker | 2022-12-20 11:25 | 1.0639 | 0 | -2
| 53 | SDFI-1896 | ABHA ID | 2022-12-18 09:23 | 12 | Blocker | 2023-01-04 10:55 | 17.0639 | 4 | 8
| 54 | SDFI-1895 | PHR APP | 2022-12-16 17:35 | 12 | Major | 2022-12-29 18:57 | 13.0569 | 0 | -2
| 55 | SDFI-1886 | PHR Web | 2022-12-16 10:17 | 12 | Blocker | 2023-01-02 13:37 | 17.1389 | 4 | 8
| 56 | SDFI-1884 | HIE-CM | 2022-12-15 19:04 | 12 | Critical | 2022-12-19 10:22 | 3.6375 | 0 | -2
| 57 | SDFI-1883 | ABHA ID | 2022-12-15 18:45 | 12 | Critical | 2023-01-10 12:52 | 25.7549 | 4 | 8
| 58 | SDFI-1873 | HIE-CM | 2022-12-15 13:46 | 12 | Blocker | 2023-01-05 15:29 | 21.0715 | 4 | 8
| 59 | SDFI-1870 | HIE-CM | 2022-12-15 09:22 | 12 | Blocker | 2022-12-20 14:24 | 5.2097 | 0 | -2
| 60 | SDFI-1867 | HIE-CM | 2022-12-14 18:36 | 12 | Blocker | 2022-12-15 10:06 | 0.64583 | 0 | -2
| 61 | SDFI-1865 | HIE-CM | 2022-12-14 17:54 | 12 | Critical | 2022-12-14 18:05 | 0.0076389 | 0 | -2
| 62 | SDFI-1842 | PHR Web | 2022-12-13 15:24 | 12 | Critical | 2023-01-03 11:50 | 20.8514 | 2 | 4
| 63 | SDFI-1781 | HIE-CM | 2022-12-08 18:22 | 12 | Blocker | 2023-01-05 15:32 | 27.8819 | 8 | 8
| 64 | SDFI-1775 | Grievance Portal | 2022-12-08 16:46 | 12 | Major | 2022-12-08 17:55 | 0.047917 | 0 | -2
| 65 | SDFI-1761 | PHR APP | 2022-12-07 14:08 | 12 | Blocker | 2022-12-20 23:03 | 13.3715 | 2 | 4
| 66 | SDFI-1749 | HIE-CM | 2022-12-06 11:58 | 12 | Minor | 2022-12-29 12:17 | 23.0132 | 0 | -2
| 67 | SDFI-1734 | HIE-CM | 2022-12-05 10:13 | 12 | Major | 2023-01-05 11:01 | 31.0333 | 0 | -2
| 68 | SDFI-1733 | PHR Web | 2022-12-04 08:36 | 12 | Blocker | 2022-12-15 14:17 | 11.2368 | 0 | -2
| 69 | SDFI-1731 | ABDM Website | 2022-12-03 10:59 | 12 | Minor | 2022-12-03 12:20 | 0.05625 | 0 | -2
| 70 | SDFI-1727 | PHR APP | 2022-12-02 12:05 | 12 | Blocker | 2022-12-02 12:59 | 0.0375 | 0 | -2
| 71 | SDFI-1695 | ABHA ID | 2022-11-29 18:04 | 11 | Major | 2022-11-30 11:57 | 0.74514 | 0 | -2
| 72 | SDFI-1694 | ABHA ID | 2022-11-29 17:36 | 11 | Critical | 2022-12-16 14:05 | 16.8535 | 0 | -2
| 73 | SDFI-1692 | HPR | 2022-11-29 17:31 | 11 | Critical | 2022-12-06 21:42 | 7.1743 | 0 | -2
| 74 | SDFI-1670 | ABHA ID | 2022-11-29 10:10 | 11 | Blocker | 2022-12-05 12:48 | 6.1097 | 0 | -2
| 75 | SDFI-1616 | ABHA ID | 2022-11-24 17:38 | 11 | Critical | 2022-12-02 11:33 | 7.7465 | 0 | -2
| 76 | SDFI-1605 | ABHA ID | 2022-11-24 16:05 | 11 | Minor | 2022-11-29 18:33 | 5.1028 | 0 | -2
| 77 | SDFI-1593 | HIE-CM | 2022-11-24 09:20 | 11 | Major | 2022-11-30 15:42 | 6.2653 | 0 | -2
| 78 | SDFI-1582 | ABHA ID | 2022-11-23 14:17 | 11 | Blocker | 2022-11-28 16:59 | 5.1125 | 0 | -2
| 79 | SDFI-1545 | ABHA ID | 2022-11-22 11:16 | 11 | Major | 2022-12-02 11:50 | 10.0236 | 0 | -2
| 80 | SDFI-1539 | HIE-CM | 2022-11-21 12:39 | 11 | Major | 2022-11-21 17:31 | 0.20278 | 0 | -2
| 81 | SDFI-1515 | HIE-CM | 2022-11-18 13:47 | 11 | Critical | 2022-12-01 16:59 | 13.1333 | 0 | -2
| 82 | SDFI-1497 | PHR APP | 2022-11-17 17:55 | 11 | Critical | 2022-12-23 10:47 | 35.7028 | 8 | 8
| 83 | SDFI-1492 | HIE-CM | 2022-11-17 14:54 | 11 | Blocker | 2022-11-25 09:59 | 7.7951 | 0 | -2
| 84 | SDFI-1456 | HIE-CM | 2022-11-16 12:06 | 11 | Blocker | 2022-11-16 13:47 | 0.070139 | 0 | -2
| 85 | SDFI-1453 | PHR APP | 2022-11-15 18:47 | 11 | Major | 2022-11-16 12:34 | 0.74097 | 0 | -2
| 86 | SDFI-1444 | ABHA ID | 2022-11-15 17:26 | 11 | Major | 2022-12-29 19:08 | 44.0708 | 2 | 4
| 87 | SDFI-1433 | HIE-CM | 2022-11-15 10:13 | 11 | Major | 2022-12-02 12:51 | 17.1097 | 0 | -2
| 88 | SDFI-1417 | ABHA ID | 2022-11-14 11:21 | 11 | Major | 2022-12-01 17:02 | 17.2368 | 0 | -2
| 89 | SDFI-1414 | PHR Web | 2022-11-14 11:17 | 11 | Major | 2023-01-05 17:47 | 52.2708 | 4 | 8
| 90 | SDFI-1712 | ABHA ID | 2022-11-14 10:29 | 11 | Critical | 2022-12-12 15:59 | 28.2292 | 4 | 8
| 91 | HPR-408 | HPR | 2022-11-30 15:38 | 11 | Major | 2022-12-28 11:03 | 27.809 | 0 | -2
Formulas:
Days Variance = IFERROR(DAYS([Resolution Date],[Created Date]), DAYS(TODAY(),[Created Date]))

## SLA-4
SLA 004- Defect count in Production environment
| Month | Current Month WAC | Baseline | Variance % | Calculation of Severity Level | Remarks | LD Points | Quarterly LD Points | Applicable LD | App Count in SLA-3
| Nov | 0.67 | NA | NA | #VALUE! | 0 is minimum cap | 0 | -1 | 0 | 8
| Dec | 0.69 | 0.82 | -15.8537 | -3.1707 | 0 is minimum cap | -3
| Jan | 0.57 | 0.69 | -17.3913 | -3.4783 | 0 is minimum cap | -3
| Feb | 0.7 | 0.57 | 22.807 | 4.5614 | 0 is minimum cap | 5
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Every increase or decrease up to 5% from baseline results in Increases or decreases by 1. However, example mentions increase or decrease by 2

## SLA-5
SLA 005- Upgrade of applications to support the (N-1) version of technology components
Production
| ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance | Appiled Severity
| GRIEVANCE PORTAL | OS | RHEL | 7.8 | 9 | OpenSource |  | No | 2
|  | Platform | PHP | 7.4 | 8.1 | OpenSource |  | Yes
|  | Platform | HTML | 5 | 5 | Standard |  | Yes
|  | Platform | Bootstrap | 3.3 | 5 | OpenSource |  | No
|  | Platform | jQuery | 2.2.4 | 3.6.1 | OpenSource |  | Yes
|  | Platform | CSS | 3 | 3 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | No
|  | DB | MySQL | 5.7.34 | 5.8 | OpenSource |  | Yes
| DASHBOARD | OS | RHEL | 7.9 | 9 | OpenSource |  | No
|  | Platform | Java (JDK) | 1.8 | 1.9 | OpenSource |  | Yes
|  | Platform | Spring Boot | 2.5.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 5.1.3 | 5 | OpenSource |  | Yes
|  | Platform | Angular | 12.1.1 | 14 | OpenSource |  | No
|  | DB | PostgreSQL | 12.3 | 15 | OpenSource |  | No
| SANDBOX | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | React JS | 16.8 | 18.2.0 | OpenSource |  | No
|  | Platform | PHP | 7 | 8.1 | OpenSource |  | Yes
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 10.1.0 | 10.1.0 | OpenSource |  | No
| HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | Yes
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | Yes
|  | Platform | PHP (Cake PHP) | 7.3.28 | 8.1 | OpenSource |  | Yes
|  | Platform | HTML | 5 | 5 | OpenSource |  | Yes
|  | Platform | CSS | 3 | 3 | OpenSource |  | Yes
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | No
| ABDM WebSite | OS | RHEL | 7.7 | 9 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.0.0 | OpenSource |  | Yes
|  | Web Server | Node Server | 16.14.2 | 19.0.1 | OpenSource |  | No
|  | Platform | HTML | 5.0 | 5.0 | Standard |  | Yes
|  | DB | PostgreSQL | 14.4 | 15 | OpenSource |  | Yes
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | Yes
|  | Platform | Java | 8 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | No
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | Yes
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | No
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Java | 8 | 19 | OpenSource |  | No
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | No
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | Yes
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | Yes
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | No
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource |  | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
| EMR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | Yes
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | No
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | No
| HFR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | Yes
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | No
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | No
| PHR App | DB | PostgreSQL | 13 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Eclipse | 21+ | 4.23 | OpenSource |  | No
|  | Application | PgAdmin | 4 | 4 | OpenSource |  | Yes
|  | Platform | Visual Studio Code | 1.6 | 1.73 | OpenSource |  | Yes
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | Yes
|  | OS | RHEL | 7.7 | 9.0 | OpenSource |  | No
|  | Platform | Android Studio | 2021.3.1 | 2021.3.1 | OpenSource |  | Yes
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | No
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | Yes
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | No
|  | Platform | Java | 11 | 19 | OpenSource |  | No
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | Yes
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | Yes
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | Yes
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | Yes
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | No
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | Yes
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | No
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | No
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | Yes
|  | Platform | .NET | 3.1 | 4.8.1 | OpenSource |  | No
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | Yes
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | Yes
Beta-Stagging
| ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance | Appiled Severity
| GRIEVANCE PORTAL | OS | RHEL | 7.9 | 9 | OpenSource |  | No | 2
|  | Platform | PHP | 7.4 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | Standard |  | YES
|  | Platform | Bootstrap | 4.3.1 | 5 | OpenSource |  | YES
|  | Platform | jQuery | 3.5.1 | 3.6.1 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
|  | DB | MySQL | 5.7.34 | 5.8 | OpenSource |  | YES
| SANDBOX | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | React JS | 16.8 | 18.2.0 | OpenSource |  | NO
|  | Platform | PHP | 7 | 8.1 | OpenSource |  | YES
|  | DB | PostgreSQL | 13 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 10.1.0 | 10.1.0 | OpenSource |  | NO
| HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | YES
|  | Platform | PHP (Cake PHP) | 7.2.32 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
| ABDM WebSite | OS | RHEL | 7.7 | 9 | OpenSource |  | NO
|  | Platform | React JS | 17.0.2 | 18.0.0 | OpenSource |  | YES
|  | Web Server | Node Server | 16.14.2 | 19.0.1 | OpenSource |  | NO
|  | Platform | HTML | 5.0 | 5.0 | Standard |  | YES
|  | DB | PostgreSQL | 14.4 | 15 | OpenSource |  | YES
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Platform | Spring Boot | 2.7.5 | 2.7.5 | OpenSource |  | YES
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | YES
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | MQ | kafka | 2.8 | 3.3.1 | OpenSource | TCL manage | No
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | No
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | NO
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | YES
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | YES
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | YES
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | YES
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | YES
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | NO
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | YES
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | No
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | No
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Rider IDE |  | 2022.2.3
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | YES
|  | Platform | .NET | 3.1 |  | OpenSource
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | YES
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | YES
Sandbox
| ABDM Building Blocks | Type | Software/Library | Running Version | Latest Version | OpenSource/Enterprise | Comments | N-1 Compliance | Appiled Severity
| HPR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO | 2
|  | OS | Cent OS | 7.6 | 8.5.2111 | OpenSource |  | YES
|  | Platform | PHP (Cake PHP) | 7.2.32 | 8.1 | OpenSource |  | YES
|  | Platform | HTML | 5 | 5 | OpenSource |  | YES
|  | Platform | CSS | 3 | 3 | OpenSource |  | YES
|  | DB | MySQL | 5.7.30 | 5.8 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4.6 | 10.1.0 | OpenSource |  | NO
| Health ID/ABHA | OS | Cent OS | 7.9 | 8.5.2111 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 16.14.0 | 18.2.0 | OpenSource |  | NO
|  |  | KeyCloak |  | 20.0.0 | OpenSource | TCL manage
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
| HPID | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | DB | PostgreSQL | 12 | 15 | OpenSource |  | NO
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource | TCL manage
|  | Platform | Spring Boot | 2.1.1 | 2.7.5 | OpenSource |  | YES
|  | Platform | Java | 8 | 19 | OpenSource |  | NO
|  | Platform | React JS | 16.13.1 | 18.2.0 | OpenSource |  | NO
|  | Platform | Redis | 6.2.1 | 7 | OpenSource |  | YES
| PHR Web | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | Cent OS | 7.9 | 9 | OpenSource |  | NO
|  | MQ | kafka | 2.8 |  | OpenSource
|  | Web Server | Tomcat Apache | 2.4 | 10.1.0 | OpenSource |  | NO
| EMR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | YES
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | YES
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | NO
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | NO
| HFR | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.3.2 | 2.7.5 | OpenSource |  | YES
|  | Platform | Bootstrap | 4 | 5 | OpenSource |  | YES
|  | Platform | Tomcat Apache | 7 | 10.1.0 | OpenSource |  | NO
|  | DB | PostgreSQL | 9.6.8 | 15 | OpenSource |  | NO
| PHR App | DB | PostgreSQL | 13 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Spring Boot | 2.5.6 | 2.7.5 | OpenSource |  | YES
|  | Platform | Eclipse | 21+ | 4.23 | OpenSource |  | NO
|  | Application | PgAdmin | 4 | 4 | OpenSource |  | YES
|  | Platform | Visual Studio Code | 1.6 | 1.73 | OpenSource |  | NO
|  | Platform | React JS | 17.0.2 | 18.2.0 | OpenSource |  | YES
|  | OS | RHEL | 7.7 | 9.0 | OpenSource |  | NO
|  | Platform | Android Studio | 2021.3.1 | 2021.3.1 | OpenSource |  | YES
| HIECM | OS | RHEL | 7.9 | 9.0 | OpenSource |  | NO
|  | Platform | IntelliJ | 2021.2.1 | 2022.2.3 | OpenSource |  | YES
|  | DB | PostgreSQL | 11 | 15 | OpenSource |  | NO
|  | Platform | Java | 11 | 19 | OpenSource |  | NO
|  | Platform | Gradle | 7.4.1 | 7.5.1 | OpenSource |  | YES
|  | Platform | Maven | 3.8.5 | 3.8.6 | OpenSource |  | YES
|  | Platform | Docker | 20.10 | 20.10 | OpenSource |  | YES
|  | Platform | Kubernetes |  | 1.25 | OpenSource
|  | Platform | Spring Boot | 2.3 | 2.7.5 | OpenSource |  | YES
|  | Platform | Redis | 5.0.3 | 7.0 | OpenSource |  | NO
|  | Platform | RabbitMQ | 3.8.4 | 3.11.2 | OpenSource |  | YES
|  | Platform | Kiali | 1.18 | 1.58.0 | OpenSource |  | NO
|  | Platform | Jaeger | 1.18 | 1.39.0 | OpenSource |  | NO
|  | Platform | Grafana | 7 | 9.2.3 | Enterprise |  | No
|  | Monitoring | Alert manager | 0.19 | 0.24 | OpenSource |  | No
|  | Platform | Kibana | 6.3 | 8.5.0 | OpenSource |  | No
|  | Platform | Prometheus | 2.5 | 2.40.1 | OpenSource |  | No
|  | Platform | Python | 3.11 | 3.11.0 | OpenSource |  | YES
|  | Platform | .NET | 3.1 | 4.8.1 | OpenSource |  | NO
|  | Platform | Postman | 9.16.0 | 10 | OpenSource |  | YES
|  | Platform | Cmder | 1.3.19 | 1.3.20 | OpenSource |  | YES

## SLA-6
SLA 006- Mobilization of all selected ‘Core’ resources as per the timeline
| SI | Name | Onboarding Date | Title | Profile Deployment Date | Quarter Start Date | Deployment Gap | Applied Severity Level | Remarks
| 1 | Jitin Chugh | 2022-10-28 | Technical Director | 2022-03-04 | 2022-11-14 | 0 | -2
| 2 | Sumit Gupta | 2022-03-04 | Project Manager | 2022-03-04 | 2022-11-14 | 0 | -2
| 3 | Amitabh Sinha | 2022-11-14 | Enterprise Architect | 2022-03-04 | 2022-11-14 | 0 | -2 | Amitabh Sinha replaced Abhishek Srivastava
| 4 | Pankaj Narang | 2022-08-01 | Technology Lead | 2022-08-01 | 2022-11-14 | 0 | -2
| 5 | Sharfuddin | 2022-07-11 | Business Process Expert (BA) | 2022-03-04 | 2022-11-14 | 0 | -2
| 6 | Pranay Goswami | 2022-10-03 | UI designer and Usability Expert | 2022-03-04 | 2022-11-14 | 0 | -2 | Pranay Goswami replaced Nilesh Mahajan
| 7 | Ankit Saxena | 2022-12-06 | IT Infra/Cloud Expert | 2022-08-05 | 2022-11-14 | 0 | -2
| 8 | Ankur Arora | 2022-09-26 | Security Expert | 2022-04-29 | 2022-11-14 | 0 | -2 | Ankur Arora replaced Abhishek Gupta
| 9 | Sanjay Rathi | 2022-12-05 | Analytics Expert | 2022-03-04 | 2022-11-14 |  | -2
| 10 | Sudhanshu Kumar | 2023-01-24 | DevOps Expert | 2022-03-04 | 2022-11-14 | 30 | 2
| 11 |  |  | Agile Lead/ Scrum Master |  | 2022-11-14
| 12 | Lovnish Bhatnagar | 2022-11-14 | Contact Center Lead | 2022-03-04 | 2022-11-14 | 0 | -2 | Lovnish Bhatnagar replaced Maneesh Sharma

## SLA-7
SLA 007- Mobilization of 100% Other resources as per the timeline
| SI. NO. | NAME | DOJ | Profile | Planned Date | Target | Applied Severity Level | Remarks
| 1 | Siddharth Asthana | 2022-03-04 | Operations Manager | 2022-11-14 | 255 | -2
| 2 | Akshay Pal | 2022-06-10 | Helpdesk Agent | 2022-11-14 | 157 | -2
| 3 | Sunil Balaram Yadav | 2022-06-15 | Helpdesk Agent | 2022-11-14 | 152 | -2
| 4 | Shalini Namdeo | 2022-05-27 | Sr. Developer | 2022-11-14 | 171 | -2
| 5 | Arpit Jain | 2022-03-21 | Sr. Developer | 2022-11-14 | 238 | -2
| 6 | Shubhanshu Shukla | 2022-05-23 | Developer | 2022-11-14 | 175 | -2
| 7 | Atik Mohammad | 2022-06-01 | Developer | 2022-11-14 | 166 | -2
| 8 | Manish16 Kumar | 2022-06-01 | Developer | 2022-11-14 | 166 | -2
| 9 | Kumar Atik | 2022-06-06 | Database Administrator | 2022-11-14 | 161 | -2
| 10 | Rajeev Ranjan | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 11 | Lata Gupta | 2022-07-19 | QA/QC Lead | 2022-11-14 | 118 | -2
| 12 | Sachin | 2022-07-19 | Developer | 2022-11-14 | 118 | -2
| 13 | Manish17 Kumar | 2022-08-17 | Developer | 2022-11-14 | 89 | -2
| 14 | Suraj Karki | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 15 | Abhimanyu Bhattar | 2022-06-15 | Sr. Developer | 2022-11-14 | 152 | -2
| 16 | Dhawal Mehta | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 17 | Pooja Rani/ Irfan | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 18 | Nikhil Vora | 2022-09-15 | Sr. Developer | 2022-11-14 | 60 | -2
| 19 | Arun H Pal | 2022-09-19 | Developer | 2022-11-14 | 56 | -2
| 20 | Mohd. Jawwad/ Karthick | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 21 | Amir Safi | 2022-06-15 | Sr. Testing Engineer | 2022-11-14 | 152 | -2
| 22 | Rajesh Verma | 2022-06-15 | Developer | 2022-11-14 | 152 | -2
| 23 | Sai Kumar Boyini | 2022-06-15 | Sr. Testing Engineer | 2022-11-14 | 152 | -2
| 24 | Deepak Singh | 2022-03-04 | Sr. Testing Engineer | 2022-11-14 | 255 | -2
| 25 | Govind Deshmukh | 2022-04-11 | Developer | 2022-11-14 | 217 | -2
| 26 | Santosh Jagtap | 2022-03-04 | Sr. Developer | 2022-11-14 | 255 | -2
| 27 | Bhavya L. | 2022-08-22 | Developer | 2022-11-14 | 84 | -2
| 28 | Naresh Banoth | 2022-04-04 | Developer | 2022-11-14 | 224 | -2
| 29 | Praveen Gupta | 2022-03-04 | Developer | 2022-11-14 | 255 | -2
| 30 | Sujit Koli | 2022-05-24 | Developer | 2022-11-14 | 174 | -2
| 31 | KrishnaD Kulkarni | 2022-08-29 | Sr. Testing Engineer | 2022-11-14 | 77 | -2
| 32 | IAAV Sireesha | 2022-08-29 | Sr. Testing Engineer | 2022-11-14 | 77 | -2
| 33 | Ganapathy P | 2022-08-10 | Sr. Developer | 2022-11-14 | 96 | -2
| 34 | Umesh P Shinde | 2022-09-23 | Sr. Developer | 2022-11-14 | 52 | -2
| 35 | Atul Kumar sharma | 2022-09-22 | Developer | 2022-11-14 | 53 | -2
| 36 | Murugan Nagarajan | 2022-06-15 | Sr. Developer | 2022-11-14 | 152 | -2
| 37 | Neelendra Pratap Singh | 2022-04-04 | Developer | 2022-11-14 | 224 | -2
| 38 | Priya Pandey | 2022-08-05 | Developer | 2022-11-14 | 101 | -2
| 40 | Narayanan Madaswamy | 2022-10-31 | Sr. Developer | 2022-11-14 | 14 | -2
| 41 | Ashish Gaharwar | 2022-10-31 | Operations Manager | 2022-11-14 | 14 | -2
| 42 | Anuj Sharma | 2022-12-01 | Developer | 2022-11-14 | -17 | -2
Formulas:
Target = DAYS([Planned Date],[DOJ])

## SLA-8
SLA 008- No. of Resource replacement in a Quarter (for ‘Core Resources’)
| SI | Title | Onboarded Resource | Exiting resource | Applied Severity Level
| 1 | Security Expert | Amitabh Sinha | Abhishek Srivastava | 0
| 2 | IT Infra/Cloud Expert | Ankit Saxena | Rajan Agarwal | 0
| 3 | DevOps Expert | Sudhanshu Kumar | Rahul Verma | 2
| 4 | Contact Center Lead | Lovnish Bhatnagar | Maneesh Sharma | 0

## SLA-9
SLA 009- Number of Resource replacement in a Quarter for (Other O& M Resources’)
| SI | Profile | Application | Onboarded Resource | Exiting resource | Applied Severity Level
| 1 | Developer | Grievance Portal | Narayanan Madaswamy | Sujeet Koli | 0
| 2 | Developer | HFR | Anuj Sharma | Bhavya L | 0

## SLA-10
SLA 010- Minimum overlap period during resource replacement
| SI | Profile | Onboarded Resource | Onboarding Date | Exiting Resource | Exit Date | Applied Severity Level
| 1 | Developer | Narayan Madaswamy | 2022-10-31 | Sujeet Koli | 2023-01-27 | 0
| 2 | Developer | Anuj Sharma | 2022-12-01 | Bhavya L | 2023-01-17 | 0
Formulas:
Applied Severity Level = IF(DAYS([Exit Date],[Onboarding Date])<=10, 2,0)

## SLA-11
SLA 011- Minimum resource availability (All resources 8*5 support resources’)
Effective working days - 65
Core | SI | Resource(s) | Date of Onboarding | Profile | Leaves Taken | Effective Workng Days | Remarks
| 1 | Jitin Chugh | 2022-10-28 | Technical Director | 5 | 57
| 2 | Sumit Gupta | 2022-03-04 | Project Manager | 0 | 65
| 3 | Amitabh Sinha | 2022-05-02 | Enterprise Architect | 1 | 65
| 4 | Panakaj Narang | 2022-08-01 | Technology Lead | 3 | 56
| 5 | Sharfuddin | 2022-07-11 | Business Process Expert (BA) | 7 | 54
| 6 | Pranay Goswami | 2022-10-03 | UI designer and Usability Expert | 3 | 57
| 7 | Rajan Agarwal/Ankit Saxena | 2022-08-05 | IT Infra/Cloud Expert | 4 | 54
| 8 | Ankur Arora | 2022-09-26 | Security Expert | 3 | 60
| 9 | Sanjay Rathi | 2022-03-04 | Analytics Expert | 2 | 31
| 10 | Rahul Verma/Sudhanshu | 2022-03-04 | DevOps Expert | 14 | 31
| 11 |  | 2022-03-04 | Agile Lead/ Scrum Master | 0 | 0
| 12 | Maneesh Sharma/Lovnish | 2022-03-04 | Contact Center Lead | 3 | 61
O&M | SI | Resource(s) | Date of Onboarding | Profile | Leaves Taken | Effective Workng Days
| 1 | Siddharth Asthana | 2022-03-04 | Operations Manager | 4 | 64
| 2 | Santosh Jagtap | 2022-03-04 | Sr. Developer | 5 | 56
| 3 | Neelendra singh | 2022-04-04 | Sr. Developer | 3 | 65
| 4 | Govind Deshmukh | 2022-04-04 | Developer | 9 | 62
| 5 | Praveen Gupta | 2022-03-04 | Developer | 5 | 63
| 6 | Shubhanshu Shukla | 2022-05-23 | Developer | 0 | 65
| 7 | Manish Kumar | 2022-06-01 | Developer | 11 | 61
| 8 | Atik Mohammad | 2022-06-01 | Developer | 1 | 65
| 9 | Suraj Singh Karki | 2022-06-15 | Developer | 2 | 64
| 10 | Kavitha HR/Dhawal | 2022-06-15 | Developer | 5 | 62
| 11 | Amir Saifi | 2022-06-15 | Sr. Testing Engineer | 5 | 61
| 12 | Rajesh Verma | 2022-06-15 | Developer | 0 | 65
| 13 | Pooja Rani/Irfan | 2022-06-15 | Developer | 5 | 63
| 14 | Mohd. Jawwad | 2022-06-15 | Developer | 6 | 62
| 15 | Amey Naik/ Murugan | 2022-09-09 | Developer | 2 | 65
| 16 | Abhimanyu Bhattar | 2022-06-15 | Sr. Developer | 10 | 57
| 17 | Sai Kumar Boyini | 2022-06-15 | Sr. Testing Engineer | 4 | 63
| 18 | Sujit Koli | 2022-06-07 | Developer | 0 | 22
| 19 | Rajeev Ranjan | 2022-06-15 | Developer | 0 | 65
| 20 | Akshay Pal | 2022-06-10 | Helpdesk Agent | 4 | 64
| 21 | Sunil Balram Yadav | 2022-06-15 | Helpdesk Agent | 4 | 63
| 22 | Kumar Atik | 2022-06-06 | Database Administrator | 2 | 65
| 23 | Arpit Jain | 2022-03-21 | Sr. Developer | 1 | 65
| 24 | Shalini Namdeo | 2022-05-27 | Developer | 8 | 60
| 25 | Sachin | 2022-07-19 | Developer | 0 | 65
| 26 | Lata Gupta | 2022-07-19 | QA/QC Lead | 4 | 63
| 27 | Naresh Banoth | 2022-04-04 | Developer | 5 | 62
| 28 | Manish Kumar | 2022-08-17 | Developer (PHP) | 0 | 65
| 29 | Bhavya L / Anuj Sharma | 2022-08-22 | Developer | 1 | 65
| 30 | Krishna D Kulkarni | 2022-08-29 | Sr. Testing Engineer | 5 | 63
| 31 | IAVV Sireesha | 2022-08-29 | Sr. Testing Engineer | 6 | 62
| 32 | Ashish Gaharwar | 2022-10-31 | Operations Manager | 2 | 65
| 33 | Nikhil Vora | 15-09-22 | Developer | 8 | 58
| 34 | Atul Kumar Sharma | 22-09-22 | Developer | 0 | 65
| 35 | Umesh P Shinde | 23-09-22 | Developer | 6 | 61
| 36 | Arun H Pal | 19-09-22 | Developer | 3 | 64
| 37 | Priya Pandey | 2022-05-08 | Developer | 7 | 61
| 38 | Ganapathy | 2022-10-08 | Developer | 2 | 65
| 39 | Deepak Singh | 2022-04-03 | Developer | 2 | 65
| 40 | Narayanan Madaswamy | 2022-10-31 | Sr. Developer | 0 | 65

## SLA-12
SLA 012- Minimum resource availability (‘24*7 support resources’)
24x7 support resources not deployed in project

## SLA-13
SLA 013- Application uptime
Target and Applied Severity Level will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications.

## SLA-14
SLA 014- Application Performance
Target and Applied Severity Level will be decided mutually by the NHA and the MSP, at the end of the Design & Development Phase after benchmarking of existing applications.

## SLA-15
SLA 015- Application Incident resolution
Target and Applied Severity Level for P1, P2, P3 and P4 incidents will be decided mutually by the NHA and the MSP at the end of the Design & Development Phase after benchmarking of existing applications.
Sr. No. | FY | Month | Date (MM/DD/YYYY) | IN NO. | Issue Type | Application impacted | Priority | Notified Time | Time stamp for allocation to L2 Technician | Response Time | Response Time SLA Met(Y / N / NA*) | Action Owner | Closure date (MM/DD/YYYY) | Closure time | Resolution Time
1 | 2022-23 | November | 2022-11-14 | IN00026 | HIE-CM Kibana and Gateway Down | HIECM | P1 | 9:30 | 10:08 | 38 Mins | Yes | TCL | Resolved | 2022-11-14 | 11:00
2 | 2022-23 | November | 2022-11-15 | IN00027 | HIE-CM Kibana and Gateway Down | HIECM | P1 | 9:58 | 10:10 | 12 Mins | Yes | TCL | Resolved | 2022-11-15 | 11:30
3 | 2022-23 | November | 2022-11-23 | IN00028 | Jenkin URL is not working | HIECM | P2 | 16:31 | 16:32 | 1 Min | Yes | TCL | Resolved | 2022-11-23 | 17:00
4 | 2022-23 | November | 2022-11-26 | IN00029 | Redis cluster down HIE-CM prod | HIECM | P2 | 0:00 | 0:30 | 30 mins | Yes | TCL | Resolved | 2022-11-26 | 10:41
5 | 2022-23 | November | 2022-11-26 | IN00030 | Devforum site down | Helpdesk HIE-CM | P1 | 20:58 | 21:13 | 15 mins | Yes | TCL | Resolved | 2022-11-27 | 0:38
6 | 2022-23 | December | 2022-12-05 | IN00031 | HIE-CM database port not connecting | HIECM | P2 | 7:48 | 8:18 | 30 Mins | Yes | TCL | Resolved | 2022-12-05 | 9:13
7 | 2022-23 | December | 2022-12-12 | IN00032 | Kibana down UAT environment | HIECM | P3 | 15:00 | 15:01 | 1 Min | Yes | TCL | Resolved | 2022-12-12 | 19:30
8 | 2022-23 | December | 2022-12-19 | IN00033 | PHR PROD server issue | PHR WEB | P1 | 9:00 | 9:30 | 30 mins | Yes | TCL | Resolved | 2022-12-19 | 11:00
9 | 2022-23 | December | 2022-12-19 | IN00034 | Sandbox DB not connected | Sandbox | P2 | 15:37 | 15:47 | 10 Mins | Yes | TCL | Resolved | 2022-12-19 | 16:37
10 | 2022-23 | December | 2022-12-19 | IN00035 | Error in Swap | HID BD(ABHA) | P2 | 20:00 | 20:05 | 05 Mins | Yes | TCL | Resolved | 2022-12-19 | 20:30
11 | 2023-24 | January | 2023-01-01 | IN00036 | API Timeout Issue | HIE-CM | P2 | 15:00 | 15:15 | 15 mins | Yes | TCL | Resolved | 2023-01-02 | 16:00
12 | 2023-24 | January | 2023-01-02 | IN00037 | Captcha Error on Sandbox | Sandbox | P2 | 15:18 | 15:28 | 10 Min | Yes | TCL | Resolved | 2023-01-02 | 22:00
13 | 2023-24 | January | 2023-01-03 | IN00038 | Sandbox CB not working : Fatal Error | Sandbox | P2 | 16:57 | 17:07 | 10 Min | Yes | TCL | Resolved | 2023-01-02 | 21:57
14 | 2023-24 | January | 2023-01-04 | IN00039 | PHR Web Server login issue | PHR WEB | P1 | 6:00 | 6:10 | 10 Min | Yes | TCL | Resolved | 2023-01-04 | 7:00
15 | 2023-24 | January | 2023-01-05 | IN00040 | Slowness issue in the API | PHR WEB | P3 | 15:30 | 15:33 | 3 mins | Yes | TCL | Resolved | 2023-01-06 | 14:00
16 | 2023-24 | January | 2023-01-09 | IN00041 | HIECM Memory Issue | HIE-CM | P2 | 9:00 | 9:10 | 10 Min | Yes | TCL | Resolved | 2023-01-09 | 11:00
17 | 2023-24 | January | 2023-01-11 | IN00042 | Redis cluster down HIE-CM prod | HIE-CM | P3 | 18:00 | 18:11 | 11 Min | Yes | TCL | Resolved | 2023-01-11 | 19:00
18 | 2023-24 | January | 2023-01-17 | IN00044 | Mail Not Received | Overall Application | P3 | 11:00 | 11:12 | 12 Mins | Yes | TCL | Resolved | 2023-01-17 | 11:39
19 | 2023-24 | January | 2023-01-17 | IN00043 | UAT Server Issue | HIE-CM | P3 | 16:22 | 16:27 | 5 Min | Yes | TCL | Resolved | 2023-01-17 | 18:00
20 | 2023-24 | January | 2023-01-23 | IN00045 | HIECM Memory Issue | HIE-CM | P3 | 10:37 | 10:47 | 10 Min | Yes | TCL | Resolved | 2023-01-23 | 17:00
21 | 2023-24 | February | 2023-02-02 | IN00046 | HICEM API Slowness | HIE-CM | P3 | 15:00 | 15:05 | 5 Min | YES | TCL | Resolved | 2023-02-02 | 16:00
22 | 2023-24 | February | 2023-02-07 | IN00047 | HIP Response timeout at Gateway | HIE-CM | P1 | 7:00 | 7:30 | 30 mins | YES | TCL | Resolved | 2023-02-07 | 11:30
23 | 2023-24 | February | 2023-02-13 | IN00047 | Token# 0 received from eHospital (Scan & Share) | HIE-CM | P1 | 7:00 | 7:30 | 30 mins | YES | TCL | Resolved | 2023-02-13 | 11:30
24 | 2023-24 | February | 2023-02-13 | IN00047 | HPID Web server went in a hung state | HPID | P1 | 13:00 | 13:30 | 30 mins | YES | TCL | Resolved | 2023-02-13 | 15:30
25 | 2023-24 | February | 2023-02-13 | IN00047 | PHR Web server went in a hung state | PHR Web | P1 | 13:00 | 13:30 | 30 mins | YES | TCL | Resolved | 2023-02-13 | 15:30
26 | 2023-24 | February | 2023-02-13 | IN00047 | Loads are not uniformly distributed on PHR Web servers | PHR Web | P1 | 7:00 | 7:30 | 30 mins | YES | TCL | Resolved | 2023-02-13 | 11:30